## 11_17_2025 Spot Hire Update
Top Hole
| Deepening | [5 empty] | *Does not include EV runs on FSVs (Mars, Turritella)*
Completion
Abandonment
Dedicated OSV
[5 empty] | 2025 |  |  | 2026
[5 empty] | November | December |  | January
Asset | Area | Activity | Start Date | End Date
Pontus (2) | Silvertip | SA10 Completion | 2025-11-07 | 2025-11-19
| Silvertip | SA013 Deepening | 2025-11-19 | 2025-12-07
| Silvertip | SA013 Completion | 2025-12-07 | 2025-12-20
| Perdido | GD003 PA | 2025-12-24 | 2026-01-02
| Perdido | GB004 PA | 2026-01-02 | 2026-01-19
| Llano | Llano 3 PA | TBD | TBD
Poseidon (3) | Whale | LWX10 Drill Top Hole | 2025-11-03 | 2025-11-13
| Whale | LWX 9 Deepening | 2025-11-13 | 2025-12-01
| Whale | LWX 8 Deepening | 2025-12-01 | 2025-12-18
Thalassa (2) | Whale | WS304 Deepening | 2025-11-03 | 2025-11-26
| Whale | WS304 Completion | 2025-11-26 | 2025-12-28
Proteus (3) | Coulomb | C3 #01 Abandonment | 2025-11-19 | 2025-12-23
| Vicksburg | VX004 Top Hole | 2025-12-23 | 2025-12-31
| Vicksburg | VX004 Deepen Hole | 2025-12-31 | 2026-02-10
Stena (2) | Sparta | SP203 15k Deepening | 2025-11-29 | 2026-01-02
| Kaikias | KI -2 Drill New Well | 2026-01-02 | 2026-03-02
Perdido | Perdido | GA10 Drilling | 2025-11-13 | 2025-12-30
Vito (1) | Mars Corridor | Channel Head Bundle Replacement | 2025-11-23 | 2025-12-02
Thalassa/Poseidon (1) | Whale | HOS Carolina - Frac Boat | 2024-07-15 | 2026-04-30
Mars (1) | Mars Corridor | A22 Drilling | 2025-11-24 | 2025-12-30
Olympus (1) | Mars Corridor | MB24 | 2025-10-15 | 2025-12-30
| Mars Corridor | Riser Swap | 2025-11-24 | 2025-11-30
ESA (1) | Central Assets | EV Run | 2025-01-01 | 2026-12-30
Appomatox, Vito, Olympus (1) | East Asset | EV Run | 2025-01-01 | 2026-12-30
Perdido/Whale (1) | West Assets | EV Run | 2025-01-01 | 2026-12-30
Q5000 | Mars Corridor | South Demos Zonal Interventions | 2025-10-01 | 2025-11-30
1
2
3
4
5
6
5
6
7
8
9
10
1
2
1
2
1
2
3
4
3
4
6
5
5
6
9
10
7
1
11
12
13
14
15
16
17
18
19
20

## 2026 Spot Hire Update
Top Hole
| Deepening |  | Dedicated Run | [15 empty] | FORECASATED JANUARY - MARCH 2026 OSV INTENSITY & SUPPORT ACTIVITIES (SPOT HIRE DRIVERS)
Completion
| Abandonment | [18 empty] | Current Fleet Profile: Core Base Fleet: 13 OSVs; Operational Spot Hires: 2 OSVs; FRAC Spot Hire: 1 OSV
Dedicated OSV
Demob
| Pilot Hole |  |  |  | 2026
| Idle |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  | December
[5 empty] | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 2 | 9 | 16 | 23 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 7 | 14 | 21 | 28
Asset | Area | Activity | Start Date | End Date
ESA, Ursa | Central Assets | EV Run | 2025-01-01 | 2026-12-30
Appomatox, Vito, Olympus | East Asset | EV Run | 2025-01-01 | 2026-12-30
Perdido/Whale | West Assets | EV Run | 2025-01-01 | 2026-12-30
Poseidon | Whale | HOS Carolina - Frac Boat | 2024-07-15 | 2026-04-30 | bar: January 5 to June 23
Pontus | Perdido | GB004 PA | 2026-01-01 | 2026-01-27 | bar: January 5 to March 23
| Sparta | Sparta Drill Pilot Hole - 006,007,008,009,010,011 | 2026-01-29 | 2026-02-12 | bar: January 5 to January 12; January 26 to March 23
| Llano | Llano PA | 2026-02-16 | 2026-03-04 | bar: January 5 to January 12; February 16 to March 23
| Stones | Stones Top Hole | 2026-03-07 | 2026-03-16 | bar: January 5 to January 12; March 16 to March 23
| Dover | DOVER DV002 Drill Sidetrack | 2026-03-31 | 2026-05-04 | bar: January 5 to May 23
| Dover | Dover 002 Completion | 2026-05-27 | 2026-06-27 | bar: January 5 to March 23; May 23 to June 23
Poseidon | Whale | LWX 8 Deepening | 2025-12-13 | 2026-01-27 | bar: January 5 to March 23
| Whale | LWX 8 Completion | 2026-01-29 | 2026-03-27 | bar: January 5 to March 23
| Whale | LWX 9 Completion | 2026-03-27 | 2026-05-10 | bar: January 5 to January 19; February 2 to February 16; March 2 to May 2
| Whale | LWX 10 Deepen Hole | 2026-05-10 | 2026-06-10 | bar: January 5 to February 23; May 9 to June 2
| Whale | LWX 10 Completion | 2026-06-10 | 2026-07-09 | bar: January 5 to February 23; June 9 to July 5
Proteus | Vicksburg | VX004 Top Hole | 2026-01-14 | 2026-01-24 | bar: January 26 to March 23
| Vicksburg | VX004 Deepen Hole | 2026-01-24 | 2026-03-07 | bar: January 12 to March 23
| Vicksburg | VX004 Completion | 2026-03-08 | 2026-03-25 | bar: January 12 to March 23
| Vicksburg | Demobilization | 2026-03-25 | TBD | bar: January 5 to April 5
Stena | Sparta | SP203 15k Deepening | 2025-12-06 | 2026-02-24 | bar: January 5 to March 23
| Kaikias | KI-2 Drill New Well | 2026-02-13 | 2026-05-18 | bar: March 2 to April 19
| Kaikias | KI-2 Completion | 2026-05-18 | 2026-06-06 | bar: April 26 to June 2
| Kaikias | Sparta SP203 Drill - Bypass | 2026-06-06 | 2026-07-08 | bar: June 2 to July 5
Thalassa | Whale | WS304 Completion | 2025-12-01 | 2026-01-22 | bar: January 5 to January 19
| Whale | Demobilization | 2025-12-28 | 2026-01-15 | bar: January 26
Vito | Mars Corridor | WF SURF | 2026-02-25 | 2026-03-31 | bar: January 5 to March 23
Perdido | Perdido | GA-23 Deepening | 2026-01-01 | 2026-03-13 | bar: January 5 to March 23
| Perdido | TAR Warehouse Boat | 2026-04-20 | 2026-05-31 | bar: April 26 to May 23
Olympus | Mars Corridor | MB24 Completion | 2026-01-01 | 2026-01-20 | bar: January 5 to January 19
| Mars Corridor | MB5 Completion | 2026-01-20 | 2026-03-24 | bar: January 26 to March 23
| Mars Corridor | MB 09 Side Track | 2026-05-15 | 2026-07-10 | bar: May 9 to July 5
Mars | Mars Corridor | A22 Completion | 2025-12-02 | 2026-01-10 | bar: January 5 to January 12
| Mars Corridor | MA17 Completion | 2026-01-10 | 2026-03-30 | bar: January 19 to March 23
| Mars Corridor | A23 Riser Swap | 2026-05-30 | 2026-06-05 | bar: May 2 to June 23
Q5000 | Whale | Whale 213, Whale 303 PLT Interventions | 2026-03-15 | 2026-04-04 | bar: March 9 to May 23
Whale | Whale | Whale TAR Warehouse Boat | 2026-04-21 | 2026-05-31 | bar: April 19 to May 23
Enchilada | Central Assets | Storm Choke well services | 2026-09-01 | 2026-12-31 | bar: September 2 to December 28
Salsa | Central Assets | Abandonment | 2026-09-01 | 2026-12-31 | bar: September 2 to December 28
Current OSV Forecasted Demand |  |  |  |  | January 5: 16 OSVs; February 2: 14 OSVs; March 2: 15 OSVs; April 5: 10 OSVs; May 2: 14 OSVs; June 2: 13 OSVs
Current OSV Base Fleet |  |  |  |  | January 5: 13 OSVs; February 2: 12 OSVs; March 2: 13 OSVs; April 5: 12 OSVs; May 2: 12 OSVs; June 2: 12 OSVs
Frac Spot Hires |  |  |  |  | January 5: 1 OSV; February 2: 1 OSV; March 2: 1 OSVs; May 2: 1 OSVs
Operational Spot Hires |  |  |  |  | January 5: 2 OSV; February 2: 2 OSV (including HOS Commander); March 2: 1 OSV (including HOS Commander)
Potential Resourcing Impacts |  |  |  |  | January 5: •Stena - Well control issues adding additional unplanned OSV demand and SP203 side track, added ~ 9 days of drilling and additional unplanned OSV demand. •Harvey Freedom (Spot Hire OSV) Planned to begin cleaning for relaease on 28 January; February 2: •Western GOA assets (Whale, Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast carry high risk of not being supported. •Timeplanner schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Pontus forecast assumes adding 3x additional Pilot Holes and Llano PA; March 2: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Pontus unknown schedule direction with Dover 002 Deepen, only accounting for 1 OSV run. •Mud Demand adding extra tension in the system, as well as supplier return constraints •Cedar Ridge moves into cleaning last week of March; April 5: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Cedar Ridge off hire starting April 1; May 2: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •HOS Carolina maintained to support Dover's swap from drilling to completions; June 2: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Stena moves down to 1 OSV after 6/15 to support Dover and Riser Swap activities •Pontus, Poseidon, and Stena each swapping from drilling to completions maintaining elevated demand •Uncertainty on competing riser swaps at Mars and Olympus with low confidence on maintaining current schedule •; September 2: Enchildada and Salsa will share a vessel 09/01/26 - 12/31/26 which will also double as a warehouse boat
1
2
3
4
1
5
6
7
6
7
5
6
10
8
11
12
9
10
9
14
15
13
16
16
1
2
3
4
9
8
12
1
2
3
4
11
12
5
14
13
9
10
11
7
5
1
2
3
1
2
3
1
2
3
1
2
3
1
2
3
1
2
3
1
2
3
1
2
3
1
2
3
14
15
4
4
5
6
8
7
8
9
10
5
6
7
8
9
10
11
13
12
4
5
6
7
8
9
10
11
12
13

## NICK
| Top Hole |  | Dedicated Run
Deepening
Completion
| Abandonment | [8 empty] | FORECASATED MARCH- MAY 2026 OSV INTENSITY & SUPPORT ACTIVITIES (SPOT HIRE DRIVERS)
Dedicated OSV
Demob
| Pilot Hole |  |  |  | March |  |  |  | April |  |  |  | May
| Idle |  |  |  | 2 | 9 | 16 | 23 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23
Asset | Area | Activity | Start Date | End Date
ESA, Ursa (1) | Central Assets | EV Run | 2025-01-01 | 2026-12-30
Appomatox, Vito, Olympus | East Asset | EV Run | 2025-01-01 | 2026-12-30
Perdido/ Whale | West Assets | EV Run | 2025-01-01 | 2026-12-30
Poseidon | Whale | HOS Carolina - Frac Boat | 2024-07-15 | 2026-04-30
Pontus | Stones | Stones Top Hole | 2026-03-07 | 2026-03-16 | bar: March 16 to March 23
| Dover | DOVER DV002 Drill Sidetrack | 2026-03-31 | 2026-05-04 | bar: March 2 to May 2
Poseidon | Whale | LWX 9 Completion | 2026-03-27 | 2026-04-28 | bar: March 2 to April 19
| Whale | LWX 10 Deepen Hole | 2026-04-28 | 2026-05-24
Proteus | Vicksburg | VX004 Completion | 2026-03-08 | 2026-03-25 | bar: March 2 to March 23
| Vicksburg | Demobilization | 2026-03-25 | TBD | bar: March 2 to April 5
Stena | Kaikias | KI-2 Drill New Well | 2026-02-13 | 2026-04-26 | bar: March 2 to April 19
| Kaikias | KI-2 Completion | 2026-04-26 | 2026-05-20
Vito | Mars Corridor | WF SURF | 2026-02-25 | 2026-03-31 | bar: March 2 to March 23
Perdido | Perdido | GA-23 Deepening | 2026-01-01 | 2026-03-13 | bar: March 2 to March 23
| Perdido | TAR Warehouse Boat | 2026-04-20 | 2026-05-31 | bar: April 26 to May 23
Olympus | Mars Corridor | MB5 Completion | 2026-01-20 | 2026-03-24
| Mars Corridor | MB 09 Riser Swap | 2026-03-11 | 2026-03-17
Mars | Mars Corridor | MA17 Completion | 2026-01-10 | 2026-03-30 | bar: March 2 to March 23
Q5000 | Whale | Whale 213, Whale 303 PLT Interventions | 2026-03-15 | 2026-04-04
Whale | Whale | Whale TAR Warehouse Boat | 2026-04-21 | 2026-05-31 | bar: March 9 to March 23; April 19 to May 23
Current OSV Forecasted Demand |  |  |  |  | March 2: 15 OSVs; April 5: 10 OSVs
Current OSV Base Fleet |  |  |  |  | March 2: 13 OSVs; April 5: 12 OSVs; May 2: 12 OSVs
Frac Spot Hires |  |  |  |  | March 2: 1 OSVs; April 5: 1 OSV; May 2: 1 OSV
Operational Spot Hires |  |  |  |  | March 2: 1 OSV (including HOS Commander); April 5: 1 OSV (HOS Brimstone)
Potential Resourcing Impacts |  |  |  |  | March 2: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Pontus unknown schedule direction with Dover 002 Deepen, only accounting for 1 OSV run. •Mud Demand adding extra tension in the system, as well as supplier return constraints •Cedar Ridge moves into cleaning last week of March; April 5: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •Cedar Ridge off hire starting April 1; May 2: •Western GOA assets (Perdido) most exposed due to 36+ hour transit times, potentially limiting one OSV run per week. •Any timeplanner changes, additional voyage needs, or increases in OSV intensity beyond what is shown in the current forecast, carry high risk of not being supported. •Schedule and run cadence must remain static to avoid capacity gaps; deviations will likely require Well & Logistics Leadership prioritization. •LImited Kabal visibility into marine demand for May, aside from TA and EV Run demand.
1
2
3
4
1
2
3
1
2
3
4
4
5
6
7
5
6
8
5
6
11
7
9
10
12
8
13
9
14
15
10
7
8
9
10

## Sheet1
Dover 2 – Logistics Risk Register
Risk ID | Logistics Area | Risk Description | Impact | Likelihood | Primary Mitigations / Controls | Logistics Owner
L‑01 | Marine / OSV | OSV not available or misaligned with frac timing required for on‑the‑fly fluid transfer during frac execution | Frac interruption, NPT, screen‑out risk | Medium–High | Lock OSV window to frac critical path; confirm vessel pumping/pressure limits; standby contingency vessel | Marine Logistics
L‑02 | Marine / OSV | Inadequate OSV capacity for ~1,500 bbl per zone (3,000 bbl total) transfer requirement | Incomplete treatment or rate throttling | Medium | Validate OSV tankage and transfer rates; sequence pre‑load vs live transfer | Marine Logistics
L‑03 | Bulk Fluids | Delayed or mis‑sequenced delivery of base oil, brines, spacers, and frac fluids | Operational delays, re‑circulation, quality risks | Medium | Phase‑based fluid delivery plan; offshore buffer volumes; firm call‑out timelines | Base & Materials
L‑04 | Bulk Fluids | Fluid contamination or off‑spec cleanliness during offshore handling and transfers | Failed tests, rework, schedule slip | Medium | Dedicated filtration units; cleanliness verification to GoM specs; controlled deck handling | Base & Rig Logistics
L‑05 | Completion Equipment | Late mobilization of unique HPHT completion equipment with limited backups | Critical‑path stoppage | Low–Medium | Early shipment; yard readiness checks; logistics tracking and fail‑to‑arrive escalation | Materials & SQ
L‑06 | Completion Equipment | Limited or no backup for select guns, screens, or DHPG equipment | Extended NPT if failure occurs | Medium | Explicit risk acceptance; confirm contingency tooling availability; pre‑run QA/QC | Materials & WTE
L‑07 | Deck Space / Lifting | Deck congestion from spoolers, sheaves, surface iron, control line reels | HSE exposure, inefficient rig ops | High | Deck layout plan; phased backload/mobilization; defined laydown zones | Rig Logistics
L‑08 | Lifting / Rig Interface | Heavy lift conflicts (sheave packages, iron, spoolers) impacting crane and Aux block availability | Non‑productive waiting, safety risk | Medium | Lift plans reviewed early; Aux block usage windows reserved | Rig & Marine

## OSV Demand Tracker
Status | Asset | Project | Activity | Base Delivery Date | Offshore Req Date | Offloading Complete Date | Estimated Duration (Hrs.) | Back to Port | Transit time back to Port | time axis 2026-01-23 to 2026-08-18
Complete | Pontus | Sparta 007 Drill Pilot Hole - | GL 01 OSV / 48 hrs / 15,000 bbl of WBM, Cement, WBM Pallet Chemicals, 1,500 Sacks of Gel, Sparta 8-1/2" BHA, Cement Head **MEET AT GB959** | 2026-01-28 | 2026-01-30 20:00 | 2026-02-01 20:00 | 48 | 2026-02-02 16:00 | 20 | bar: 2026-01-28 to 2026-02-02
Complete | Pontus | Sparta 008 Drill Pilot Hole | GL 01a OSV / 12 hrs / 2,500 bbl of 16 ppg WBM (BBL COULD INCREASE) | 2026-02-01 | 2026-02-04 01:30 | 2026-02-04 13:30 | 12 | 2026-02-05 09:30 | 20 | bar: 2026-02-01 to 2026-02-05
Complete | Pontus | Llano LL003 Abandonment | GL 01 OSV / 24 hours / Millout BHA, BOP Test Tools, LDS Recovery Tools, 4-1/2" DP | 2026-02-12 | 2026-02-15 18:00 | 2026-02-16 18:00 | 24 | 2026-02-17 12:00 | 18 | bar: 2026-02-12 to 2026-02-17
Complete | Pontus | Llano LL003 Abandonment | GL 01a OSV / 12 hrs / Loadmaster Container, Perdido Fluid Transfer | 2026-02-17 | 2026-02-18 | 2026-02-19 12:00 | 36 | 2026-02-20 06:00 | 18 | bar: 2026-02-17 to 2026-02-20
Complete | Pontus | Llano LL003 Abandonment | GL 03 OSV / 24 hrs / 7-3/4" CIBP, MI Pallet Chemicals & Barite GL 06 OSV / 36 hrs / 13-5/8" Casing Tools, WBCO BHA, 16" CIBP, 22" Plug, Backload 13-5/8" Casing | 2026-02-19 | 2026-02-23 04:00 | 2026-02-24 16:00 | 36 | 2026-02-25 10:00 | 18 | bar: 2026-02-19 to 2026-02-25
Complete | Pontus | Llano LL003 Abandonment | GL 04 OSV / 36 hours / SBM Chemicals, 10-3/4" Casing Tools, ASA Tools, Backload 10-3/4" Casing | 2026-02-23 | 2026-02-26 11:15 | 2026-02-27 23:15 | 36 | 2026-02-28 17:15 | 18 | bar: 2026-02-23 to 2026-02-28
Complete | Pontus | Llano LL003 Abandonment | GL 06 OSV / 36 hrs / 13-5/8" Casing Tools, WBCO BHA, 16" CIBP, 22" Plug, Backload 13-5/8" Casing | 2026-02-26 | 2026-03-01 09:00 | 2026-03-02 21:00 | 36 | 2026-03-03 15:00 | 18 | bar: 2026-02-26 to 2026-03-03
Complete | Pontus | Stones 20 Top Hole | GL 01 OSV / 36 hrs / 10,000 bbl of 16 ppg WBM, WBM Chemicals, 38" Jet Pipe, 28" Casing, Jetting / 32" BHA, LPWHH, Casing Tools | 2026-03-03 | 2026-03-05 18:00 | 2026-03-07 06:00 | 36 | 2026-03-08 02:00 | 20 | bar: 2026-03-03 to 2026-03-08
Complete | Pontus | Stones 20 Top Hole | GL 02 OSV / 36 hrs / 14,000 bbl of 16 ppg WBM, 26" BHA, 28" Casing Tools, 28" Backups | 2026-03-06 | 2026-03-09 20:45 | 2026-03-11 08:45 | 36 | 2026-03-12 04:45 | 20 | bar: 2026-03-06 to 2026-03-12
Complete | Pontus | Stones 20 Top Hole | GL 03 OSV / 24 hrs / 22" Casing, 22" Casing Tools, 22" Backups | 2026-03-09 | 2026-03-12 18:45 | 2026-03-13 18:45 | 24 | 2026-03-14 14:45 | 20 | bar: 2026-03-09 to 2026-03-14
Complete | Pontus | Dover 2 ST01BP01 | GL 01 OSV / 36 hrs / Weekly Groceries & Rig Supplies, SPM, Umbilical, Spooler **MEET RIG AT WR508** | 2026-03-17 | 2026-03-19 22:00 | 2026-03-21 10:00 | 36 | 2026-03-22 04:00 | 18 | bar: 2026-03-17 to 2026-03-22
Complete | Pontus | Dover 2 ST01BP01 | GL 02 OSV / 36 hrs/ SBM Chemicals / 9-3/8" Casing **MEET at Grand Isle 061** | 2026-03-24 | 2026-03-26 04:00 | 2026-03-27 16:00 | 36 | 2026-03-28 10:00 | 18 | bar: 2026-03-24 to 2026-03-28
Complete | Pontus | Dover 2 ST01BP01 | GL 03 OSV / 24hrs / SBM/ THS and WH Adapter / Cleanout BHA / Drill Pipe/ Cement *Meet at GI061* | 2026-03-27 | 2026-03-29 12:00 | 2026-03-30 12:00 | 24 | 2026-03-31 06:00 | 18 | bar: 2026-03-27 to 2026-03-31
Complete | Pontus | Dover 2 ST01BP01 | GL 07 OSV / 36 hrs / 9-7/8" x 11" Drill Ahead BHA, 9-3/8" / NXT / Background Pallet Chemicals | 2026-04-13 | 2026-04-15 03:00 | 2026-04-16 15:00 | 36 | 2026-04-17 09:00 | 18 | bar: 2026-04-13 to 2026-04-17
Complete | Pontus | Dover 2 ST01BP01 | GL 09 OSV/ 36 hrs / 8-5/8" x 7-3/4" liner and Casing Tools -- Backload 9-7/8" x 11" BHA / 9-3/8" Pipe, Hanger Basket, Casing Tools and Accessories | 2026-04-26 | 2026-04-28 18:00 | 2026-04-30 06:00 | 36 | 2026-05-01 | 18 | bar: 2026-04-26 to 2026-05-01
Complete | Pontus | Dover 2 ST01BP01 | GL 11 OSV / 36 hrs / Weekly Groceries & Rig Supplies--Backload 4,000bbls of 13.1# SBM | 2026-04-29 | 2026-05-01 06:00 | 2026-05-02 18:00 | 36 | 2026-05-03 12:00 | 18 | bar: 2026-04-29 to 2026-05-03
Complete | Pontus | Dover 2 ST01BP01 | GL 13 OSV / 16 hrs / Drill Water & **Primary Function to Backload 6,000 bbls SBM for Well Displacement** | 2026-05-13 | 2026-05-14 | 2026-05-14 16:00 | 16 | 2026-05-15 10:00 | 18 | bar: 2026-05-13 to 2026-05-15
Complete | Pontus | Dover 002 Completion | GL 01 OSV / 36 hrs / 9,000 bb of 14.4 ppg Brine, Brine Chemicals, Completion DP, Filtration, WBCO, HPDU, HPDU Iron | 2026-05-11 | 2026-05-13 18:00 | 2026-05-15 06:00 | 36 | 2026-05-16 | 18 | bar: 2026-05-11 to 2026-05-16
Complete | Poseidon | Whale 8 Completion | GL 01a OSV / 48hrs - WBCO / HPDU / 3" Iron (HPDU) | 2026-01-24 | 2026-01-26 05:12 | 2026-01-28 05:12 | 48 | 2026-01-30 05:12 | 48 | bar: 2026-01-24 to 2026-01-30
Complete | Poseidon | Whale 8 Completion | GL 02 OSV / 36hrs - SLB TCP / Supreme TCP Iron/Head / HES Deburr | 2026-01-31 | 2026-02-04 06:00 | 2026-02-05 18:00 | 36 | 2026-02-07 18:00 | 48 | bar: 2026-01-31 to 2026-02-07
Complete | Poseidon | Whale 8 Completion | GL 04 OSV / 24hrs - MST and Frac Equipment | 2026-02-04 | 2026-02-08 01:30 | 2026-02-09 01:30 | 24 | 2026-02-11 01:30 | 48 | bar: 2026-02-04 to 2026-02-11
Complete | Poseidon | Whale 8 Completion | GL 06 OSV- THS and TA Equipment, FLDCO Equipment **VESSEL NEEDS TO HAVE BRINE TANKS** | 2026-02-19 | 2026-02-22 06:00 | 2026-02-23 06:00 | 24 | 2026-02-25 06:00 | 48 | bar: 2026-02-19 to 2026-02-25
Complete | Poseidon | Whale 8 Completion | GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment / Packer Fluid | 2026-02-24 | 2026-02-26 12:00 | 2026-02-28 12:00 | 48 | 2026-03-02 12:00 | 48 | bar: 2026-02-24 to 2026-03-03
Complete | Poseidon | Whale 8 Completion | GL 10 OSV / 48hrs - Power Wire / SSXT | 2026-03-15 | 2026-03-18 05:00 | 2026-03-20 05:00 | 48 | 2026-03-22 05:00 | 48 | bar: 2026-03-14 to 2026-03-22
Complete | Poseidon | Whale 8 Completion | GL 11 OSV / 48hrs: THS (LWX9) SBM / Base Oil- Backload Completions Equipment | 2026-03-19 | 2026-03-23 06:45 | 2026-03-24 06:45 | 24 | 2026-03-26 06:45 | 48 | bar: 2026-03-19 to 2026-03-26
Complete | Poseidon | Whale 9 Completion | GL 01 OSV / 72hrs - Brine / DE / WBCO | 2026-03-27 | 2026-03-29 23:59 | 2026-04-01 23:59 | 72 | 2026-04-03 23:59 | 48 | bar: 2026-03-27 to 2026-04-03
Complete | Poseidon | Whale 9 Completion | GL 03 OSV / 36hrs - SLB TCP / Supreme TCP Iron/Head / HES Deburr | 2026-04-06 | 2026-04-08 22:00 | 2026-04-10 10:00 | 36 | 2026-04-12 10:00 | 48 | bar: 2026-04-06 to 2026-04-12
Complete | Poseidon | Whale 9 Completion | GL 03a OSV / 4hrs: Shared run w/ Perdido for HES Debris Tank | 2026-04-08 | 2026-04-09 23:00 | 2026-04-10 03:00 | 4 | 2026-04-12 03:00 | 48 | bar: 2026-04-08 to 2026-04-12
Complete | Poseidon | Whale 9 Completion | GL 04 OSV / 48hrs - MST / Frac Equipment / CaCl2 | 2026-04-13 | 2026-04-15 12:00 | 2026-04-16 12:00 | 24 | 2026-04-18 12:00 | 48 | bar: 2026-04-13 to 2026-04-18
Complete | Poseidon | Whale 9 Completion | GL 04b OSV / 24hrs: Shared Vessel for MST Equipment | 2026-04-13 | 2026-04-16 02:00 | 2026-04-17 02:00 | 24 | 2026-04-19 02:00 | 48 | bar: 2026-04-13 to 2026-04-19
Complete | Poseidon | Whale 9 Completion | GL 05 HOS Carolina / 120hrs - Frac Heads & THS | 2026-04-16 | 2026-04-19 13:45 | 2026-04-24 13:45 | 120 | 2026-04-26 13:45 | 48 | bar: 2026-04-16 to 2026-04-26
Complete | Poseidon | Whale 9 Completion | GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment / Packer Fluid GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment | 2026-04-26 | 2026-04-29 06:15 | 2026-05-01 06:15 | 48 | 2026-05-03 06:15 | 48 | bar: 2026-04-26 to 2026-05-03
Complete | Poseidon | Whale 9 Completion | GL 10 OSV / 48hrs- Power Wire / SSXT | 2026-04-30 | 2026-05-03 06:15 | 2026-05-05 06:15 | 48 | 2026-05-07 06:15 | 48 | bar: 2026-04-30 to 2026-05-07
Complete | Poseidon | Whale 10 Deepening | GL 01 OSV / 72 HRS: Post Spud Equipment / 14 CSG / 22" Stormpacker / SBM / Barite / Base Oil | 2026-05-08 | 2026-05-10 07:00 | 2026-05-13 07:00 | 72 | 2026-05-15 07:00 | 48 | bar: 2026-05-08 to 2026-05-15
Complete | Poseidon | Whale 10 Deepening | GL 02 OSV / 48 HRS: 18.125" BHA / Cutting Boxes / Liner Hanger / Cement | 2026-05-14 | 2026-05-16 06:00 | 2026-05-18 06:00 | 48 | 2026-05-20 06:00 | 48 | bar: 2026-05-14 to 2026-05-20
Complete | Poseidon | Whale 10 Deepening | GL 03 OSV / 72 HRS: 12.25" BHA / 9 5/8" Liner / Run Equipment | 2026-05-25 | 2026-05-27 13:00 | 2026-05-29 13:00 | 48 | 2026-05-31 13:00 | 48 | bar: 2026-05-23 to 2026-05-29
Complete | Poseidon | Whale 10 Deepening | GL 03a OSV / 48 hrs: Groceries / Resupply / GTM-69 DP | 2026-05-25 | 2026-05-27 06:00 | 2026-05-29 06:00 | 48 | 2026-05-31 06:00 | 48 | bar: 2026-05-25 to 2026-05-31
Planned | Poseidon | Whale 10 Deepening | GL 05 OSV / 48 HRS: Tieback / Liner Hanger / Run Equipment / Cement | 2026-06-09 | 2026-06-12 02:45 | 2026-06-14 02:45 | 48 | 2026-06-16 02:45 | 48 | bar: 2026-05-29 to 2026-06-05
Planned | Poseidon | Whale 10 Completion | GL 01 OSV / 72hrs - Brine / DE / WBCO / THS | 2026-06-16 | 2026-06-19 01:15 | 2026-06-22 01:15 | 72 | 2026-06-24 01:15 | 48 | bar: 2026-06-07 to 2026-06-15
Planned | Poseidon | Whale 10 Completion | GL 02 OSV-WBCO / HPDU / 3" Iron / Tetra Filtration | 2026-06-19 | 2026-06-21 16:30 | 2026-06-23 16:30 | 48 | 2026-06-25 16:30 | 48 | bar: 2026-06-12 to 2026-06-18
Planned | Poseidon | Whale 10 Completion | GL 04 OSV- SLB TCP / Supreme TCP Iron/Head / HES Deburr / Brine | 2026-06-25 | 2026-06-28 07:30 | 2026-07-01 07:30 | 72 | 2026-07-03 07:30 | 48 | bar: 2026-06-16 to 2026-06-24
Planned | Poseidon | Whale 10 Completion | GL 05 OSV- MST / Frac Equipment | 2026-06-30 | 2026-07-02 23:15 | 2026-07-03 23:15 | 24 | 2026-07-05 23:15 | 48 | bar: 2026-06-20 to 2026-06-26
Planned | Poseidon | Whale 10 Completion | GL 06 HOS Carolina / 120 hrs - Frac Heads | 2026-07-05 | 2026-07-07 16:00 | 2026-07-12 16:00 | 120 | 2026-07-14 16:00 | 48 | bar: 2026-06-25 to 2026-07-05
Planned | Poseidon | Whale 10 Completion | GL 07 OSV- ROCS / Upper Completions Equipment / Packer Fluid | 2026-07-08 | 2026-07-10 16:00 | 2026-07-12 16:00 | 48 | 2026-07-14 16:00 | 48 | bar: 2026-06-28 to 2026-07-05
Planned | Poseidon | Whale 10 Completion | GL 08 OSV/FSV- Power Wire / Tree | 2026-07-12 | 2026-07-14 16:00 | 2026-07-16 16:00 | 48 | 2026-07-18 16:00 | 48 | bar: 2026-07-02 to 2026-07-09
Complete | Proteus | VX004 Deepen | GL 01 OSV - SBM 16" Casing, RB Tools, CMT, Barite, FMC Tools | 2026-01-24 | 2026-01-26 13:15 | 2026-01-27 13:15 | 24 | 2026-01-28 05:15 | 16 | bar: 2026-01-24 to 2026-01-28
Complete | Proteus | VX004 Deepen | GL 02a OSV - Contigency 18" String, 18" Run Tools | 2026-01-30 | 2026-01-31 00:30 | 2026-02-01 00:30 | 24 | 2026-02-01 16:30 | 16 | bar: 2026-01-30 to 2026-02-01
Complete | Proteus | VX004 Deepen | GL 04 OSV - 14-3/4" BHA, 12-1/4" Casing & RB Tools, Centralizers, SBM | 2026-01-31 | 2026-02-02 04:15 | 2026-02-03 04:15 | 24 | 2026-02-03 20:15 | 16 | bar: 2026-01-31 to 2026-02-03
Complete | Proteus | VX004 Deepen | GL 05 OSV - 12/1/4" Hanger, 12-1/4" Run Toos, RTTS, Cement Head / Swage | 2026-02-04 | 2026-02-06 17:00 | 2026-02-07 17:00 | 24 | 2026-02-08 09:00 | 16 | bar: 2026-02-04 to 2026-02-08
Complete | Proteus | VX004 Deepen | GL 06a OSV - Tri-State, 8-5/8" Casing, RB Tools, SBM, Barite, CMT | 2026-02-09 | 2026-02-12 | 2026-02-13 | 24 | 2026-02-13 16:00 | 16 | bar: 2026-02-09 to 2026-02-13
Complete | Proteus | VX004 Deepen | GL 07 OSV - 8-5/8" Hanger, 8-5/8" Run Tools, THS & Tools | 2026-02-15 | 2026-02-16 14:00 | 2026-02-17 14:00 | 24 | 2026-02-18 06:00 | 16 | bar: 2026-02-15 to 2026-02-18
Complete | Proteus | VX004 Deepen | GL 08 OSV - Backload SBM, DP, Metrology | 2026-02-19 | 2026-02-22 01:15 | 2026-02-23 01:15 | 24 | 2026-02-23 17:15 | 16 | bar: 2026-02-19 to 2026-02-23
Complete | Proteus | VX004 Deepen | GL 09 OSV - WBCO BHA, DIF, Rig Chem, Tubing | 2026-02-21 | 2026-02-23 19:15 | 2026-02-24 19:15 | 24 | 2026-02-25 11:15 | 16 | bar: 2026-02-21 to 2026-02-25
Complete | Proteus | VX004 Deepen | GL 10 OSV - SBM Backload, 6-3/4" BHA | 2026-02-26 | 2026-02-28 10:45 | 2026-03-01 10:45 | 24 | 2026-03-02 02:45 | 16 | bar: 2026-02-26 to 2026-03-02
Complete | Proteus | VX004 Deepen | GL 11 OSV - Brine, HPDU, Filtration, GT-M69 | 2026-02-28 | 2026-03-01 12:45 | 2026-03-02 12:45 | 24 | 2026-03-03 04:45 | 16 | bar: 2026-02-28 to 2026-03-03
Complete | Proteus | VX004 Completion | GL 01 OSV - Lower Completion Tools | 2026-03-03 | 2026-03-05 17:15 | 2026-03-06 17:15 | 24 | 2026-03-07 09:15 | 16 | bar: 2026-03-03 to 2026-03-07
Complete | Proteus | VX004 Completion | GL 02 OSV - WBCU & WBRR BHAs / DIF Backload | 2026-03-08 | 2026-03-11 16:30 | 2026-03-12 16:30 | 24 | 2026-03-13 08:30 | 16 | bar: 2026-03-08 to 2026-03-13
Complete | Proteus | VX004 Completion | GL 03 OSV - Upper Completion Tools (Packer Fluid) | 2026-03-11 | 2026-03-14 20:00 | 2026-03-15 20:00 | 24 | 2026-03-16 12:00 | 16 | bar: 2026-03-11 to 2026-03-16
Complete | Proteus | VX004 Completion | GL 05 OSV - Tree / Backload (B/H CaBr & NaBr) | 2026-03-18 | 2026-03-20 04:30 | 2026-03-21 04:30 | 24 | 2026-03-21 20:30 | 16 | bar: 2026-03-18 to 2026-03-21
Complete | Proteus | VX004 Completion | GL 06 OSV - Backload Completion Equipment | 2026-03-22 | 2026-03-24 16:30 | 2026-03-25 16:30 | 24 | 2026-03-26 08:30 | 16 | bar: 2026-03-22 to 2026-03-26
Complete | Proteus | DEMOB | GL 01 OSV - Backload CML/ROV/DP | 2026-03-28 | 2026-03-30 | 2026-03-31 | 24 | 2026-03-31 03:00 | 3 | bar: 2026-03-28 to 2026-03-31
Complete | Proteus | DEMOB | GL 02 OSV - Backload Riser | 2026-03-31 | 2026-04-01 04:00 | 2026-04-02 04:00 | 24 | 2026-04-02 07:00 | 3 | bar: 2026-03-31 to 2026-04-02
Complete | Stena Evolution | Sparta SP203 Deepening | GL 09e OSV - 30 Hours -6k bbls 16.3 PPG SBM/ 5000k SXS Barite / Misc. | 2026-01-23 | 2026-01-27 06:00 | 2026-01-28 18:00 | 36 | 2026-01-29 13:00 | 19 | bar: 2026-01-23 to 2026-01-29
Complete | Stena Evolution | Sparta SP203 Deepening | GL 09g OSV - 60 Hours -Backload Casing/ Demob Vessel / Backload SBM | 2026-02-07 | 2026-02-09 06:00 | 2026-02-11 06:00 | 48 | 2026-02-12 01:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10 OSV - 36 Hours - Wireline Equipment / Bridge Plug / Pipe Racks Excess 10.50" & 11.25" Casing / B/L SBM?? | 2026-02-15 | 2026-02-18 06:48 | 2026-02-19 18:48 | 36 | 2026-02-20 13:48 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10b OSV- 12 Hours - Class H Cement Blend (Sparta Specific) | 2026-01-30 | 2026-02-02 02:00 | 2026-02-02 14:00 | 12 | 2026-02-03 09:00 | 19 | bar: 2026-01-30 to 2026-02-03
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10c OSV- 24 Hours- 6K bbls SBM / 4k sxs Barite | 2026-02-02 | 2026-02-03 06:00 | 2026-02-04 06:00 | 24 | 2026-02-05 01:00 | 19 | bar: 2026-02-02 to 2026-02-05
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10e OSV- 24 Hours- Groceries / Rig Supplies / 6-5/8" DP (60 Jnts) | 2026-02-06 | 2026-02-07 07:00 | 2026-02-08 07:00 | 24 | 2026-02-09 02:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10f OSV - 30 Hours - THS Install / Misc. GL 11 OSV - 30 Hours - THS Install / Misc. | 2026-02-19 | 2026-02-21 11:30 | 2026-02-22 17:30 | 30 | 2026-02-23 12:30 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 12 OSV - 50 Hours - Demob / Backload SBM / RCS Pit Cleaning Equipment/Backload DP | 2026-02-20 | 2026-02-22 11:30 | 2026-02-24 13:30 | 50 | 2026-02-25 08:30 | 19
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 01 OSV 60 Hours - 38", 32", / 32" & 29" BHA/ LPWHH FMC Equip. | 2026-02-12 | 2026-02-15 03:48 | 2026-02-17 15:48 | 60 | 2026-02-18 00:48 | 9 | bar: 2026-02-12 to 2026-02-18
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 02 OSV- 50 Hours - 28" Casing/ WBM/ FOAM Equipment/16 PPG WBM/ Class H Cmt | 2026-02-13 | 2026-02-16 21:54 | 2026-02-18 23:54 | 50 | 2026-02-19 08:54 | 9 | bar: 2026-02-13 to 2026-02-19
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 03 OSV 60 Hours - 22" Casing 26"x28" BHA / WBM / Cement / Pallet Material | 2026-02-16 | 2026-02-19 19:30 | 2026-02-22 07:30 | 60 | 2026-02-22 16:30 | 9 | bar: 2026-02-16 to 2026-02-23
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 03b OSV - 24 Hours - 10k-12k WBM / Groceries / Rig Supplies GL 03a OSV - 24 Hours - 10k-12k WBM | 2026-02-17 | 2026-02-20 06:15 | 2026-02-21 06:15 | 24 | 2026-02-21 15:15 | 9 | bar: 2026-02-18 to 2026-02-23
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 04 OSV - 48 Hours - 10k-12-k WBM / Class H Cement | 2026-02-18 | 2026-02-21 12:15 | 2026-02-23 12:15 | 48 | 2026-02-23 21:15 | 9 | bar: 2026-02-19 to 2026-02-25
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 05 OSV - 60 Hours - 18" Casing / 18-1/8" X 21" BHA / SBM / Cement | 2026-02-24 | 2026-02-27 05:15 | 2026-03-01 17:15 | 60 | 2026-03-02 02:15 | 9 | bar: 2026-02-24 to 2026-03-02
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 05a OSV - 30 hrs - BHA/Csg Tools/Pallet Material/Misc. | 2026-03-04 | 2026-03-06 14:00 | 2026-03-07 20:00 | 30 | 2026-03-08 05:00 | 9 | bar: 2026-03-04 to 2026-03-08
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 06 OSV 60 Hours- 16-1/2" BHA / 14" Casing / SBM / Barite / Class H Cmt - BL 10.05" Csg & Excess 18" Csg | 2026-03-04 | 2026-03-06 21:00 | 2026-03-09 09:00 | 60 | 2026-03-09 18:00 | 9 | bar: 2026-03-04 to 2026-03-09
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 06c OSV - 48 Hours - 14" Casing Overflow | 2026-03-07 | 2026-03-10 16:00 | 2026-03-12 16:00 | 48 | 2026-03-13 01:00 | 9 | bar: 2026-03-07 to 2026-03-13
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07 OSV 60 Hours- 12 1/4" BHA / 11-7/8" Casing / SBM / Barite / TXI Cmt | 2026-03-14 | 2026-03-17 15:00 | 2026-03-20 03:00 | 60 | 2026-03-20 12:00 | 9 | bar: 2026-03-14 to 2026-03-20
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07b OSV - 24 Hours - 5k bbls -14.1 ppg SBM | 2026-03-18 | 2026-03-20 | 2026-03-21 | 24 | 2026-03-21 09:00 | 9 | bar: 2026-03-18 to 2026-03-21
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07d OSV 3 Hours - Stena (5) Jnts 6-5/8" HDWP / SLB B/U BHA (Share to Drop Off, If Available) | 2026-03-18 | 2026-03-19 06:00 | 2026-03-19 09:00 | 3 | 2026-03-19 18:00 | 9 | bar: 2026-03-18 to 2026-03-19
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07f OSV- 24 hrs- Backload Wireline Equipment / Groceries / Rig Supplies/ BL Riser | 2026-03-31 | 2026-04-01 22:00 | 2026-04-02 22:00 | 24 | 2026-04-03 07:00 | 9 | bar: 2026-03-31 to 2026-04-03
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08 OSV - 60 Hours - 10-5/8" BHA / 7-5/8" Liner | 2026-04-08 | 2026-04-09 17:00 | 2026-04-12 05:00 | 60 | 2026-04-12 14:00 | 9 | bar: 2026-04-08 to 2026-04-12
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08b OSV - 36 Hours - 1900 BBLS 11.9 SBM Riding / Backload 14.3 SBM / Backload (5) Jnts Riser / Misc. | 2026-04-13 | 2026-04-15 13:00 | 2026-04-17 01:00 | 36 | 2026-04-17 10:00 | 9 | bar: 2026-04-13 to 2026-04-17
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08f OSV 3 Hours - SLB BHA / WFR Fishing Tools / Cutting Boxes (Share to Drop Off) | 2026-04-19 | 2026-04-20 22:00 | 2026-04-21 01:00 | 3 | 2026-04-21 10:00 | 9 | bar: 2026-04-19 to 2026-04-21
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 09 OSV- 30 hrs- Misc. / BH 14.2 SBM / BH Excess 11-7/8" Csg | 2026-04-27 | 2026-04-29 10:57 | 2026-04-30 16:57 | 30 | 2026-05-01 01:57 | 9 | bar: 2026-04-27 to 2026-05-01
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 09b 0SV - 50 hrs - 7-5/8" x 10-3/4" Tieback Liner / BH Remaining 14.2 SBM | 2026-04-30 | 2026-05-05 05:00 | 2026-05-06 11:00 | 30 | 2026-05-06 20:00 | 9 | bar: 2026-04-30 to 2026-05-06
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 10 OSV - 48 Hours - Workstrings 4-1/2", 6-5/8" DP / Demob Misc. Equipment | 2026-05-09 | 2026-05-12 07:00 | 2026-05-14 19:00 | 60 | 2026-05-15 04:00 | 9 | bar: 2026-05-09 to 2026-05-15
Complete | Stena Evolution | Kaikias Completion | GL 01 OSV - 60 Hours - THS / Brine / Filtration / Misc. | 2026-05-12 | 2026-05-15 22:45 | 2026-05-18 10:45 | 60 | 2026-05-18 19:45 | 9 | bar: 2026-05-12 to 2026-05-18
Complete | Stena Evolution | Kaikias Completion | GL 03 OSV 48 Hours - WBRT / HES CPS / HES CWT/4-1/2" Production Tbg/Sump Packer/ CIBP / Wireline | 2026-05-20 | 2026-05-23 16:15 | 2026-05-24 16:15 | 24 | 2026-05-25 01:15 | 9 | bar: 2026-05-20 to 2026-05-25
Complete | Stena Evolution | Kaikias Completion | GL 04 OSV- 24 Hours - TCP / Lower Completion / Backload (11-12K) 11.9 PPG SBM & Trash Fluid | 2026-05-21 | 2026-05-24 17:30 | 2026-05-26 17:30 | 48 | 2026-05-27 02:30 | 9 | bar: 2026-05-21 to 2026-05-27
Complete | Stena Evolution | Kaikias Completion | GL 05 OSV - 48 hrs- FMC / ROCS / Superior / Halliburton CPS & WBCO / SLB Prod. Pkr. / NaCl/MEG 8.9 | 2026-05-31 | 2026-06-03 09:00 | 2026-06-05 09:00 | 48 | 2026-06-05 18:00 | 9 | bar: 2026-05-27 to 2026-06-01
Planned | Stena Evolution | Kaikias Completion | GL 07 OSV - 48 Hours - SSXT | 2026-06-07 | 2026-06-09 20:21 | 2026-06-11 20:21 | 48 | 2026-06-12 05:21 | 9 | bar: 2026-06-03 to 2026-06-08
Planned | Stena Evolution | Sparta SP203- Bypass | GL 01 OSV-36 Hours- Packer Retrieval / WBCO / SBM / Cement / Drill Pipe | 2026-06-12 | 2026-06-15 18:00 | 2026-06-17 06:00 | 36 | 2026-06-18 01:00 | 19 | bar: 2026-06-05 to 2026-06-11
Planned | Stena Evolution | Sparta SP203- Bypass | GL 03 OSV-60 Hours- 10.05" Doubles & Singles / Cement | 2026-06-22 | 2026-06-25 00:45 | 2026-06-27 12:45 | 60 | 2026-06-28 07:45 | 19 | bar: 2026-06-17 to 2026-06-21
Planned | Stena Evolution | Sparta SP203- Bypass | GL 04 OSV-48 Hours- Tieback Casing | 2026-06-27 | 2026-06-30 14:45 | 2026-07-02 14:45 | 48 | 2026-07-03 09:45 | 19 | bar: 2026-06-21 to 2026-06-27
Planned | Stena Evolution | Sparta SP203- Bypass | GL 04a OSV 30 Hours - Expert Riser (21 joints Riser) | 2026-07-03 | 2026-07-04 14:45 | 2026-07-05 20:45 | 30 | 2026-07-06 15:45 | 19 | bar: 2026-06-27 to 2026-06-30
Planned | Stena Evolution | Sparta SP203- Bypass | GL 05 OSV-36 Hours- Tubing Head Spool | 2026-07-04 | 2026-07-07 06:48 | 2026-07-08 18:48 | 36 | 2026-07-09 13:48 | 19 | bar: 2026-07-04 to 2026-07-09
Complete | Q5000 | Whale WN213 PLT | OSV #1 - 50 hrs Mobilize | 2026-03-14 | 2026-03-15 08:00 | 2026-03-17 08:00 | 48 | 2026-03-17 11:00 | 3 | bar: 2026-03-14 to 2026-03-17
Complete | Q5000 | Whale WN213 PLT | OSV #2- 36 hrs Mobilize and Transit | 2026-03-16 | 2026-03-17 08:00 | 2026-03-18 20:00 | 36 | 2026-03-18 23:00 | 3 | bar: 2026-03-16 to 2026-03-18
Complete | Q5000 | Whale WN213 PLT | OSV - Latch and Test IRS - Brine, W/L Tools | 2026-03-20 | 2026-03-22 08:00 | 2026-03-27 08:00 | 120 | 2026-03-29 04:00 | 44 | bar: 2026-03-20 to 2026-03-27
Complete | Q5000 | Whale WN303 PLT | GL 06 PLT B/h Base/Crude | 2026-03-31 | 2026-04-02 12:00 | 2026-04-06 12:00 | 96 | 2026-04-08 08:00 | 44 | bar: 2026-03-31 to 2026-04-08
Complete | Q5000 | URSA Princess P002 Zonal Isolation | OSV 60 hrs - CT, Fluids, CMT | 2026-04-12 | 2026-04-13 21:00 | 2026-04-15 21:00 | 48 | 2026-04-16 06:00 | 9 | bar: 2026-04-12 to 2026-04-16
Complete | Q5000 | URSA Princess P002 Zonal Isolation | Rig Up America with Tank Package | 2026-03-27 | 2026-04-20 01:00 | 2026-04-24 01:00 | 96 | 2026-04-24 10:00 | 9 | 2026-04-17: Rig Up Tank Package
Complete | Q5000 | Princess P101 | GL17a Milk Run | 2026-04-30 | 2026-05-02 06:00 | 2026-05-04 06:00 | 48 | 2026-05-04 16:00 | 10 | bar: 2026-04-30 to 2026-05-04
Planned | Noble Voyager | Voyager Arrival in GoA | GL 03 OSV - Landing String, Grocereiss, Supplies | 2026-07-13 | 2026-07-14 06:00 | 2026-07-16 06:00 | 48 | 2026-07-16 16:00 | 10 | bar: 2026-07-13 to 2026-07-16
Planned | Noble Voyager | Princess P13 - Top Hole | GL 01 OSV - 36hrs - 38 & 32" Csg, LPWH Tools, CTRS, WBM, CMT | 2026-07-17 | 2026-07-20 | 2026-07-21 12:00 | 36 | 2026-07-21 22:00 | 10 | bar: 2026-07-17 to 2026-07-21
Planned | Noble Voyager | Princess P13 - Top Hole | GL 03 OSV - 60hrs - WBM, Foam & N2 Equip, 28" Csg, CTRS, WH Tools | 2026-07-21 | 2026-07-23 | 2026-07-25 12:00 | 60 | 2026-07-25 22:00 | 10 | bar: 2026-07-21 to 2026-07-25
Planned | Noble Voyager | Princess P13 - Top Hole | GL 06 OSV - 72hrs - WBM, CMT, 22" Csg, HPWHH, Empty Baskets | 2026-07-23 | 2026-07-25 | 2026-07-28 | 72 | 2026-07-28 10:00 | 10 | bar: 2026-07-23 to 2026-07-28
Planned | Noble Voyager | Princess P13 - Top Hole | GL 07 OSV - 72hrs - WBM, Empty Baskets, N2 Tanks, Foam Chemical | 2026-07-25 | 2026-07-27 | 2026-07-30 | 72 | 2026-07-30 10:00 | 10 | bar: 2026-07-25 to 2026-07-30
Planned | Noble Voyager | Princess P13 - Top Hole | GL 08 OSV - 60hrs - Backload WBM & Equipment | 2026-07-26 | 2026-07-28 | 2026-07-30 12:00 | 60 | 2026-07-30 22:00 | 10 | bar: 2026-07-26 to 2026-07-30
Planned | Noble Voyager | Princess P8 TA - Prep for Sidetrack | GL 01 OSV - 36hrs - SBM, Barite, CMT, BOPA, WH Tools, WBCO, 4-1/2" & 3-1/2" DP | 2026-07-29 | 2026-07-30 | 2026-07-31 12:00 | 36 | 2026-07-31 22:00 | 10 | bar: 2026-07-29 to 2026-07-31
Planned | Noble Voyager | Princess P8 TA - Prep for Sidetrack | GL 02 OSV - WL Unit, Whipstock/Mills, Gyro, EZSVs, 10-3/4" Brute Pkr | 2026-08-07 | 2026-08-09 04:00 | 2026-08-10 16:00 | 36 | 2026-08-11 02:00 | 10 | bar: 2026-08-07 to 2026-08-11
Planned | Noble Voyager | Princess P8 Drill - Sidetrack 02 - | GL 01 OSV - 30hrs - 6.25" BHAs, 5-1/2" Csg, Cents | 2026-08-12 | 2026-08-13 10:00 | 2026-08-14 16:00 | 30 | 2026-08-15 02:00 | 10 | bar: 2026-08-12 to 2026-08-15
Planned | Mars | A23 Decomplete | GL 02 OSV_ 48 hrs. POOH with current tubing and accessories | 2026-05-17 | 2026-05-18 00:30 | 2026-05-20 00:30 | 48 | 2026-05-20 10:30 | 10 | bar: 2026-05-17 to 2026-05-20
Planned | Mars | A23 Decomplete | GL 03 OSV - 60hrs - .Set EZSV-B Cement Retainer, SpotBalanced Plug | 2026-05-20 | 2026-05-22 18:00 | 2026-05-25 06:00 | 60 | 2026-05-25 16:00 | 10 | bar: 2026-05-20 to 2026-05-25
Planned | Mars | A23 Slot Recovery | GL 02 OSV - 80hrs - Cut Tiebacks and Pull Upper Tieback | 2026-05-26 | 2026-05-28 18:00 | 2026-06-01 02:00 | 80 | 2026-06-01 02:00 | 10 | bar: 2026-05-26 to 2026-06-01
Planned | Mars | A23 Slot Recovery | GL 04 OSV - 100hrs - Pull Production Riser | 2026-05-28 | 2026-05-30 06:00 | 2026-06-03 10:00 | 100 | 2026-06-01 02:00 | 10 | bar: 2026-05-28 to 2026-06-01
Planned | Olympus | MB 09 | GL 05b Backhaul ODR to Core | 2026-06-14 | 2026-06-16 21:00 | 2026-06-23 21:00 | 168 | 2026-06-24 21:00 | 24 | bar: 2026-06-14 to 2026-06-24
Planned | Olympus | MB 09 | GL 05c Outer Production Riser | 2026-06-16 | 2026-06-19 09:00 | 2026-06-26 09:00 | 168 | 2026-06-27 09:00 | 24 | bar: 2026-06-16 to 2026-06-27
Complete | Q5000 | P101 | IWOCS, SLB CT | 2026-05-20 | 2026-05-22 | 2026-05-22 10:00 | 10 | 2026-05-22 20:00 | 10
Complete | Q5000 | P101 | Crawfish Run (Crew Boat) | 2026-05-21 | 2026-05-23 | 2026-05-22 10:00 | 5 | 2026-05-22 15:00 | 5
Complete | Q5000 | P101 | GL09 Milk Run (Crew Boat) | 2026-05-24 | 2026-05-26 | 2026-05-26 05:00 | 5 | 2026-05-26 10:00 | 5
Complete | Q5000 | P101 | MC940 Vito- GL01 Mobilize/Transit | 2026-05-28 | 2026-05-30 | 2026-05-30 10:00 | 10 | 2026-05-30 20:00 | 10
Planned | ESA | P&A | 2026 Well Services | 2026-08-27 | 2026-09-01 06:00 | 2027-01-01 06:00 | 2928 | 2027-01-01 14:00 | 8 | bar: 2026-05-26 to 2026-06-01
Planned | Pontus | Sisco 001 Drill | GL 01 OSV / 24 hrs / 10,000 bbl of 16 ppg WBM, WBM Chemicals, 38" Jet Pipe; Jet & 32" BHA, 38" LPWHH, 38" Casing Tools, 28" Casing, Class H Cement | 2026-06-05 | 2026-06-07 17:15 | 2026-06-08 17:15 | 24 | 2026-06-09 09:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 02 OSV / 24 hrs / 26" BHA, 28" Conductor, 28" Casing Tools, 28" Backups, 5,000 bbl of 16 ppg WBM | 2026-06-07 | 2026-06-09 19:15 | 2026-06-10 19:15 | 24 | 2026-06-11 11:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 04 OSV / 36 hrs / 10,000 bbl of 16 ppg WBM, 22" Casing, 22" Casing Tools, 22" HPWHH | 2026-06-10 | 2026-06-12 22:30 | 2026-06-14 10:30 | 36 | 2026-06-15 02:30 | 16
Planned | Pontus | Sisco 001 Drill | GL 05 OSV / 24 hrs / TBD bbl of TBD ppg SBM, SBM Chemicals, 18-1/8" x 21" BHA, 18" Casing, 18" Liner Hanger | 2026-06-16 | 2026-06-18 08:15 | 2026-06-19 08:15 | 24 | 2026-06-20 00:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 08 OSV / 24 hrs / 16-1/2" x 19" BHA, 16" Casing, 16" Rack Back Tools, 16" Liner Hanger | 2026-06-24 | 2026-06-26 00:44 | 2026-06-27 00:44 | 24 | 2026-06-27 16:44 | 16
Planned | Pontus | Sisco 001 Drill | GL 12 OSV / 24 hrs / 14-3/4" BHA, 12-1/4" & 11.97" Casing, Casing Rack Back Tools, 12-1/4" Hanger | 2026-07-02 | 2026-07-04 16:31 | 2026-07-05 16:31 | 24 | 2026-07-06 08:31 | 16
Planned | Pontus | Sisco 001 Drill | GL 14 OSV / 24 hrs / 9-7/8" x 11-1/2" BHA, 9-3/8" Casing, Casing Rack Back Tools, 9-3/8" Liner Hanger | 2026-07-09 | 2026-07-11 04:57 | 2026-07-12 04:57 | 24 | 2026-07-12 20:57 | 16
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
[6 empty] | 0 |  | 0
Note on H23: Author: Assuming 24 hr loadout
Note on H26: Author: Assuming 24 hr loadout

## Vessel Schedule
| November |  |  |  | December |  |  |  | January
| Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Vessel 1 | December Week 2: EV West
Vessel 2 | December Week 2: EV East
Vessel 3 | December Week 2: EV Central
Vessel 4 | December Week 2: Mars Drilling
Vessel 5 | December Week 2: Olympus Drilling
Vessel 6 | December Week 2: Perdido Drilling
Vessel 7 | December Week 2: Stena Eveloution
Vessel 8 | December Week 2: Deepwater Poseidon
Vessel 9 | December Week 2: Deepwater Pontus
Vessel 10 | December Week 2: Deepwater Proteus
Vessel 11 | December Week 2: Thalassa; January Week 1: Stena; January Week 2: Stena
Vessel 12 |  | Q5000 |  |  | Stena | Stena | Stena | Stena | Stena | Stena | Stena | Stena
Vessel 13 |  |  | Vito | Vito |  | Pontus | Pontus | Pontus | Pontus | Pontus | Pontus | Pontus
Spot Hire 1 |  |  |  | Olympus | Proteus | Proteus | Proteus | Proteus | Proteus | Proteus | Proteus | Proteus
Spot Hire 2 | November Week 1: Poseidon; November Week 2: Poseidon; November Week 4: Pontus; December Week 3: Proteus; December Week 4: Proteus; January Week 1: Proteus
Spot Hire 3 | Poseidon | Poseidon |  | Poseidon | Poseidon | Poseidon | Poseidon | Poseidon | Poseidon | Poseidon | Poseidon | Poseidon
Spot Hire 4 | November Week 3: Thalassa; November Week 4: Thalassa; December Week 1: Thalassa; December Week 2: Thalassa; December Week 3: Thalassa; December Week 4: Thalassa
Spot Hire 5 | November Week 3: Stena; November Week 4: Stena