## Project Summary
SPARTA 20K DEEPENING & COMPLETION WELL
OSV BOAT PLAN - PROJECT SUMMARY
PROJECT DETAILS
Port Location: | Fourchon, LA
Rig Location: | Sparta
Transit Time: | 36 hours (each way)
Port Loading Time: | 72 hours
Offloading Time: | 12-18 hours
Deepening Phase: | December 24, 2026 - January 24, 2027 (32 days)
Completion Phase: | January 1, 2027 - February 23, 2027 (54 days)
Overlap Period: | January 1-24, 2027 (24 days - CRITICAL)
Total Program Duration: | 86 days
OSV FLEET CONFIGURATION
Vessel ID | Primary Role | Capacity | Total Trips | Status
OSV-1 | SLB Bulk Fluids | 8,000 bbls | 12 | Primary
OSV-2 | Tetra Bulk Fluids | 8,000 bbls | 13 | Primary
OSV-3 | Drill Pipe & Equipment | 5,000 sq ft deck | 8 | Primary
OSV-4 | Heavy Cargo & Mixed | 7,000 bbls + 4,000 sq ft | 10 | Primary
OSV-5 | Standby/Peak Support | Flex capacity | 3 | Standby (Jan 1-24)
FSV-1 | Weekly Consumables | 2,500 sq ft + 500 bbls | 12 | Weekly Runs
CARGO SUMMARY
Cargo Type | Quantity | Supplier/Source | Vessel Assignment
Bulk Fluids (SLB) | 16,350 bbls | SLB | OSV-1
Bulk Fluids (Tetra) | 15,071-16,571 bbls | Tetra | OSV-2
Drill Pipe | ~35,257 feet | Stena/Workstrings | OSV-3
MPT Tanks | 14 x 25-bbl + 1 tote | Tetra | OSV-3/4
Consumables | Various | Multiple | OSV-4
ESTIMATED PROGRAM COST
4 Primary OSVs (86 days): | $5.16M - $8.6M
Standby Vessel (24 days): | $360K - $600K
FSV Weekly Runs (86 days): | $688K - $1.03M
TOTAL PROGRAM ESTIMATE: | $6.2M - $10.2M

## Detailed Schedule
Trip # | Vessel | Activity | Start Date | End Date | Duration (Days) | Load Location | Discharge Location | Cargo Type | Status | Notes
1 | OSV-1 | Loading at Port | 2026-12-21 | 2026-12-24 | 3 | Fourchon | - | SLB Fluids | Planned
1 | OSV-1 | Transit & Offload | 2026-12-24 | 2026-12-27 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
2 | OSV-1 | Loading at Port | 2026-12-28 | 2026-12-31 | 3 | Fourchon | - | SLB Fluids | Planned
2 | OSV-1 | Transit & Offload | 2026-12-31 | 2027-01-03 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
3 | OSV-1 | Loading at Port | 2027-01-04 | 2027-01-07 | 3 | Fourchon | - | SLB Fluids | Planned
3 | OSV-1 | Transit & Offload | 2027-01-07 | 2027-01-10 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
4 | OSV-1 | Loading at Port | 2027-01-11 | 2027-01-14 | 3 | Fourchon | - | SLB Fluids | Planned
4 | OSV-1 | Transit & Offload | 2027-01-14 | 2027-01-17 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
5 | OSV-1 | Loading at Port | 2027-01-18 | 2027-01-21 | 3 | Fourchon | - | SLB Fluids | Planned
5 | OSV-1 | Transit & Offload | 2027-01-21 | 2027-01-24 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
6 | OSV-1 | Loading at Port | 2027-01-25 | 2027-01-28 | 3 | Fourchon | - | SLB Fluids | Planned
6 | OSV-1 | Transit & Offload | 2027-01-28 | 2027-01-31 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
7 | OSV-1 | Loading at Port | 2027-02-01 | 2027-02-04 | 3 | Fourchon | - | SLB Fluids | Planned
7 | OSV-1 | Transit & Offload | 2027-02-04 | 2027-02-07 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
8 | OSV-1 | Loading at Port | 2027-02-08 | 2027-02-11 | 3 | Fourchon | - | SLB Fluids | Planned
8 | OSV-1 | Transit & Offload | 2027-02-11 | 2027-02-14 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
9 | OSV-1 | Loading at Port | 2027-02-15 | 2027-02-18 | 3 | Fourchon | - | SLB Fluids | Planned
9 | OSV-1 | Transit & Offload | 2027-02-18 | 2027-02-21 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
10 | OSV-1 | Loading at Port | 2027-02-22 | 2027-02-25 | 3 | Fourchon | - | SLB Fluids | Planned
10 | OSV-1 | Transit & Offload | 2027-02-25 | 2027-02-28 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
11 | OSV-1 | Loading at Port | 2027-03-01 | 2027-03-04 | 3 | Fourchon | - | SLB Fluids | Planned
11 | OSV-1 | Transit & Offload | 2027-03-04 | 2027-03-07 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
12 | OSV-1 | Loading at Port | 2027-03-08 | 2027-03-11 | 3 | Fourchon | - | SLB Fluids | Planned
12 | OSV-1 | Transit & Offload | 2027-03-11 | 2027-03-14 | 3 | Fourchon | Sparta Rig | SLB Fluids | Planned | 36h transit + 12-18h offload
13 | OSV-2 | Loading at Port | 2026-12-21 | 2026-12-24 | 3 | Fourchon | - | Tetra Fluids | Planned
13 | OSV-2 | Transit & Offload | 2026-12-24 | 2026-12-27 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
14 | OSV-2 | Loading at Port | 2026-12-28 | 2026-12-31 | 3 | Fourchon | - | Tetra Fluids | Planned
14 | OSV-2 | Transit & Offload | 2026-12-31 | 2027-01-03 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
15 | OSV-2 | Loading at Port | 2027-01-04 | 2027-01-07 | 3 | Fourchon | - | Tetra Fluids | Planned
15 | OSV-2 | Transit & Offload | 2027-01-07 | 2027-01-10 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
16 | OSV-2 | Loading at Port | 2027-01-11 | 2027-01-14 | 3 | Fourchon | - | Tetra Fluids | Planned
16 | OSV-2 | Transit & Offload | 2027-01-14 | 2027-01-17 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
17 | OSV-2 | Loading at Port | 2027-01-18 | 2027-01-21 | 3 | Fourchon | - | Tetra Fluids | Planned
17 | OSV-2 | Transit & Offload | 2027-01-21 | 2027-01-24 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
18 | OSV-2 | Loading at Port | 2027-01-25 | 2027-01-28 | 3 | Fourchon | - | Tetra Fluids | Planned
18 | OSV-2 | Transit & Offload | 2027-01-28 | 2027-01-31 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
19 | OSV-2 | Loading at Port | 2027-02-01 | 2027-02-04 | 3 | Fourchon | - | Tetra Fluids | Planned
19 | OSV-2 | Transit & Offload | 2027-02-04 | 2027-02-07 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
20 | OSV-2 | Loading at Port | 2027-02-08 | 2027-02-11 | 3 | Fourchon | - | Tetra Fluids | Planned
20 | OSV-2 | Transit & Offload | 2027-02-11 | 2027-02-14 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
21 | OSV-2 | Loading at Port | 2027-02-15 | 2027-02-18 | 3 | Fourchon | - | Tetra Fluids | Planned
21 | OSV-2 | Transit & Offload | 2027-02-18 | 2027-02-21 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
22 | OSV-2 | Loading at Port | 2027-02-22 | 2027-02-25 | 3 | Fourchon | - | Tetra Fluids | Planned
22 | OSV-2 | Transit & Offload | 2027-02-25 | 2027-02-28 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
23 | OSV-2 | Loading at Port | 2027-03-01 | 2027-03-04 | 3 | Fourchon | - | Tetra Fluids | Planned
23 | OSV-2 | Transit & Offload | 2027-03-04 | 2027-03-07 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
24 | OSV-2 | Loading at Port | 2027-03-08 | 2027-03-11 | 3 | Fourchon | - | Tetra Fluids | Planned
24 | OSV-2 | Transit & Offload | 2027-03-11 | 2027-03-14 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
25 | OSV-2 | Loading at Port | 2027-03-15 | 2027-03-18 | 3 | Fourchon | - | Tetra Fluids | Planned
25 | OSV-2 | Transit & Offload | 2027-03-18 | 2027-03-21 | 3 | Fourchon | Sparta Rig | Tetra Fluids | Planned | 36h transit + 12-18h offload
26 | OSV-3 | Loading at Port | 2026-12-20 | 2026-12-23 | 3 | Fourchon | - | Drill Pipe | Planned
26 | OSV-3 | Transit & Offload | 2026-12-23 | 2026-12-26 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
27 | OSV-3 | Loading at Port | 2026-12-27 | 2026-12-30 | 3 | Fourchon | - | Drill Pipe | Planned
27 | OSV-3 | Transit & Offload | 2026-12-30 | 2027-01-02 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
28 | OSV-3 | Loading at Port | 2027-01-03 | 2027-01-06 | 3 | Fourchon | - | Drill Pipe | Planned
28 | OSV-3 | Transit & Offload | 2027-01-06 | 2027-01-09 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
29 | OSV-3 | Loading at Port | 2027-01-10 | 2027-01-13 | 3 | Fourchon | - | Drill Pipe | Planned
29 | OSV-3 | Transit & Offload | 2027-01-13 | 2027-01-16 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
30 | OSV-3 | Loading at Port | 2027-01-17 | 2027-01-20 | 3 | Fourchon | - | Drill Pipe | Planned
30 | OSV-3 | Transit & Offload | 2027-01-20 | 2027-01-23 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
31 | OSV-3 | Loading at Port | 2027-01-24 | 2027-01-27 | 3 | Fourchon | - | Drill Pipe | Planned
31 | OSV-3 | Transit & Offload | 2027-01-27 | 2027-01-30 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
32 | OSV-3 | Loading at Port | 2027-01-31 | 2027-02-03 | 3 | Fourchon | - | Drill Pipe | Planned
32 | OSV-3 | Transit & Offload | 2027-02-03 | 2027-02-06 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
33 | OSV-3 | Loading at Port | 2027-02-07 | 2027-02-10 | 3 | Fourchon | - | Drill Pipe | Planned
33 | OSV-3 | Transit & Offload | 2027-02-10 | 2027-02-13 | 3 | Fourchon | Sparta Rig | Drill Pipe | Planned | 36h transit + 12-18h offload
34 | OSV-4 | Loading at Port | 2026-12-22 | 2026-12-25 | 3 | Fourchon | - | Heavy Cargo | Planned
34 | OSV-4 | Transit & Offload | 2026-12-25 | 2026-12-28 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
35 | OSV-4 | Loading at Port | 2026-12-29 | 2027-01-01 | 3 | Fourchon | - | Heavy Cargo | Planned
35 | OSV-4 | Transit & Offload | 2027-01-01 | 2027-01-04 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
36 | OSV-4 | Loading at Port | 2027-01-05 | 2027-01-08 | 3 | Fourchon | - | Heavy Cargo | Planned
36 | OSV-4 | Transit & Offload | 2027-01-08 | 2027-01-11 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
37 | OSV-4 | Loading at Port | 2027-01-12 | 2027-01-15 | 3 | Fourchon | - | Heavy Cargo | Planned
37 | OSV-4 | Transit & Offload | 2027-01-15 | 2027-01-18 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
38 | OSV-4 | Loading at Port | 2027-01-19 | 2027-01-22 | 3 | Fourchon | - | Heavy Cargo | Planned
38 | OSV-4 | Transit & Offload | 2027-01-22 | 2027-01-25 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
39 | OSV-4 | Loading at Port | 2027-01-26 | 2027-01-29 | 3 | Fourchon | - | Heavy Cargo | Planned
39 | OSV-4 | Transit & Offload | 2027-01-29 | 2027-02-01 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
40 | OSV-4 | Loading at Port | 2027-02-02 | 2027-02-05 | 3 | Fourchon | - | Heavy Cargo | Planned
40 | OSV-4 | Transit & Offload | 2027-02-05 | 2027-02-08 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
41 | OSV-4 | Loading at Port | 2027-02-09 | 2027-02-12 | 3 | Fourchon | - | Heavy Cargo | Planned
41 | OSV-4 | Transit & Offload | 2027-02-12 | 2027-02-15 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
42 | OSV-4 | Loading at Port | 2027-02-16 | 2027-02-19 | 3 | Fourchon | - | Heavy Cargo | Planned
42 | OSV-4 | Transit & Offload | 2027-02-19 | 2027-02-22 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
43 | OSV-4 | Loading at Port | 2027-02-23 | 2027-02-26 | 3 | Fourchon | - | Heavy Cargo | Planned
43 | OSV-4 | Transit & Offload | 2027-02-26 | 2027-03-01 | 3 | Fourchon | Sparta Rig | Heavy Cargo | Planned | 36h transit + 12-18h offload
44 | OSV-5 | Loading at Port | 2027-01-05 | 2027-01-08 | 3 | Fourchon | - | Standby | Planned
44 | OSV-5 | Transit & Offload | 2027-01-08 | 2027-01-11 | 3 | Fourchon | Sparta Rig | Standby | Planned | 36h transit + 12-18h offload
45 | OSV-5 | Loading at Port | 2027-01-12 | 2027-01-15 | 3 | Fourchon | - | Standby | Planned
45 | OSV-5 | Transit & Offload | 2027-01-15 | 2027-01-18 | 3 | Fourchon | Sparta Rig | Standby | Planned | 36h transit + 12-18h offload
46 | OSV-5 | Loading at Port | 2027-01-19 | 2027-01-22 | 3 | Fourchon | - | Standby | Planned
46 | OSV-5 | Transit & Offload | 2027-01-22 | 2027-01-25 | 3 | Fourchon | Sparta Rig | Standby | Planned | 36h transit + 12-18h offload
47 | FSV-1 | Loading at Port | 2026-12-24 | 2026-12-26 | 2 | Fourchon | - | Weekly Consumables | Planned
47 | FSV-1 | Transit & Offload | 2026-12-26 | 2026-12-29 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
48 | FSV-1 | Loading at Port | 2026-12-31 | 2027-01-02 | 2 | Fourchon | - | Weekly Consumables | Planned
48 | FSV-1 | Transit & Offload | 2027-01-02 | 2027-01-05 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
49 | FSV-1 | Loading at Port | 2027-01-07 | 2027-01-09 | 2 | Fourchon | - | Weekly Consumables | Planned
49 | FSV-1 | Transit & Offload | 2027-01-09 | 2027-01-12 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
50 | FSV-1 | Loading at Port | 2027-01-14 | 2027-01-16 | 2 | Fourchon | - | Weekly Consumables | Planned
50 | FSV-1 | Transit & Offload | 2027-01-16 | 2027-01-19 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
51 | FSV-1 | Loading at Port | 2027-01-21 | 2027-01-23 | 2 | Fourchon | - | Weekly Consumables | Planned
51 | FSV-1 | Transit & Offload | 2027-01-23 | 2027-01-26 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
52 | FSV-1 | Loading at Port | 2027-01-28 | 2027-01-30 | 2 | Fourchon | - | Weekly Consumables | Planned
52 | FSV-1 | Transit & Offload | 2027-01-30 | 2027-02-02 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
53 | FSV-1 | Loading at Port | 2027-02-04 | 2027-02-06 | 2 | Fourchon | - | Weekly Consumables | Planned
53 | FSV-1 | Transit & Offload | 2027-02-06 | 2027-02-09 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
54 | FSV-1 | Loading at Port | 2027-02-11 | 2027-02-13 | 2 | Fourchon | - | Weekly Consumables | Planned
54 | FSV-1 | Transit & Offload | 2027-02-13 | 2027-02-16 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
55 | FSV-1 | Loading at Port | 2027-02-18 | 2027-02-20 | 2 | Fourchon | - | Weekly Consumables | Planned
55 | FSV-1 | Transit & Offload | 2027-02-20 | 2027-02-23 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
56 | FSV-1 | Loading at Port | 2027-02-25 | 2027-02-27 | 2 | Fourchon | - | Weekly Consumables | Planned
56 | FSV-1 | Transit & Offload | 2027-02-27 | 2027-03-02 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
57 | FSV-1 | Loading at Port | 2027-03-04 | 2027-03-06 | 2 | Fourchon | - | Weekly Consumables | Planned
57 | FSV-1 | Transit & Offload | 2027-03-06 | 2027-03-09 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)
58 | FSV-1 | Loading at Port | 2027-03-11 | 2027-03-13 | 2 | Fourchon | - | Weekly Consumables | Planned
58 | FSV-1 | Transit & Offload | 2027-03-13 | 2027-03-16 | 2 | Fourchon | Sparta Rig | Weekly Consumables | Planned | 24-28h transit + 6-8h offload (FSV)

## Vessel Tracker
Date | Vessel ID | Current Status | Current Location | ETA Next Port | Cargo Loaded | Cargo Discharged | Delays (Hours) | Weather Hold | Comments
2026-12-20 | OSV-1 | [5 empty] | 0 | No
2026-12-20 | OSV-2 | [5 empty] | 0 | No
2026-12-20 | OSV-3 | [5 empty] | 0 | No
2026-12-20 | OSV-4 | [5 empty] | 0 | No
2026-12-20 | OSV-5 | [5 empty] | 0 | No
2026-12-20 | FSV-1 | [5 empty] | 0 | No
2026-12-21 | OSV-1 | [5 empty] | 0 | No
2026-12-21 | OSV-2 | [5 empty] | 0 | No
2026-12-21 | OSV-3 | [5 empty] | 0 | No
2026-12-21 | OSV-4 | [5 empty] | 0 | No
2026-12-21 | OSV-5 | [5 empty] | 0 | No
2026-12-21 | FSV-1 | [5 empty] | 0 | No
2026-12-22 | OSV-1 | [5 empty] | 0 | No
2026-12-22 | OSV-2 | [5 empty] | 0 | No
2026-12-22 | OSV-3 | [5 empty] | 0 | No
2026-12-22 | OSV-4 | [5 empty] | 0 | No
2026-12-22 | OSV-5 | [5 empty] | 0 | No
2026-12-22 | FSV-1 | [5 empty] | 0 | No
2026-12-23 | OSV-1 | [5 empty] | 0 | No
2026-12-23 | OSV-2 | [5 empty] | 0 | No
2026-12-23 | OSV-3 | [5 empty] | 0 | No
2026-12-23 | OSV-4 | [5 empty] | 0 | No
2026-12-23 | OSV-5 | [5 empty] | 0 | No
2026-12-23 | FSV-1 | [5 empty] | 0 | No
2026-12-24 | OSV-1 | [5 empty] | 0 | No
2026-12-24 | OSV-2 | [5 empty] | 0 | No
2026-12-24 | OSV-3 | [5 empty] | 0 | No
2026-12-24 | OSV-4 | [5 empty] | 0 | No
2026-12-24 | OSV-5 | [5 empty] | 0 | No
2026-12-24 | FSV-1 | [5 empty] | 0 | No
2026-12-25 | OSV-1 | [5 empty] | 0 | No
2026-12-25 | OSV-2 | [5 empty] | 0 | No
2026-12-25 | OSV-3 | [5 empty] | 0 | No
2026-12-25 | OSV-4 | [5 empty] | 0 | No
2026-12-25 | OSV-5 | [5 empty] | 0 | No
2026-12-25 | FSV-1 | [5 empty] | 0 | No
2026-12-26 | OSV-1 | [5 empty] | 0 | No
2026-12-26 | OSV-2 | [5 empty] | 0 | No
2026-12-26 | OSV-3 | [5 empty] | 0 | No
2026-12-26 | OSV-4 | [5 empty] | 0 | No
2026-12-26 | OSV-5 | [5 empty] | 0 | No
2026-12-26 | FSV-1 | [5 empty] | 0 | No
2026-12-27 | OSV-1 | [5 empty] | 0 | No
2026-12-27 | OSV-2 | [5 empty] | 0 | No
2026-12-27 | OSV-3 | [5 empty] | 0 | No
2026-12-27 | OSV-4 | [5 empty] | 0 | No
2026-12-27 | OSV-5 | [5 empty] | 0 | No
2026-12-27 | FSV-1 | [5 empty] | 0 | No
2026-12-28 | OSV-1 | [5 empty] | 0 | No
2026-12-28 | OSV-2 | [5 empty] | 0 | No
2026-12-28 | OSV-3 | [5 empty] | 0 | No
2026-12-28 | OSV-4 | [5 empty] | 0 | No
2026-12-28 | OSV-5 | [5 empty] | 0 | No
2026-12-28 | FSV-1 | [5 empty] | 0 | No
2026-12-29 | OSV-1 | [5 empty] | 0 | No
2026-12-29 | OSV-2 | [5 empty] | 0 | No
2026-12-29 | OSV-3 | [5 empty] | 0 | No
2026-12-29 | OSV-4 | [5 empty] | 0 | No
2026-12-29 | OSV-5 | [5 empty] | 0 | No
2026-12-29 | FSV-1 | [5 empty] | 0 | No
2026-12-30 | OSV-1 | [5 empty] | 0 | No
2026-12-30 | OSV-2 | [5 empty] | 0 | No
2026-12-30 | OSV-3 | [5 empty] | 0 | No
2026-12-30 | OSV-4 | [5 empty] | 0 | No
2026-12-30 | OSV-5 | [5 empty] | 0 | No
2026-12-30 | FSV-1 | [5 empty] | 0 | No
2026-12-31 | OSV-1 | [5 empty] | 0 | No
2026-12-31 | OSV-2 | [5 empty] | 0 | No
2026-12-31 | OSV-3 | [5 empty] | 0 | No
2026-12-31 | OSV-4 | [5 empty] | 0 | No
2026-12-31 | OSV-5 | [5 empty] | 0 | No
2026-12-31 | FSV-1 | [5 empty] | 0 | No
2027-01-01 | OSV-1 | [5 empty] | 0 | No
2027-01-01 | OSV-2 | [5 empty] | 0 | No
2027-01-01 | OSV-3 | [5 empty] | 0 | No
2027-01-01 | OSV-4 | [5 empty] | 0 | No
2027-01-01 | OSV-5 | [5 empty] | 0 | No
2027-01-01 | FSV-1 | [5 empty] | 0 | No
2027-01-02 | OSV-1 | [5 empty] | 0 | No
2027-01-02 | OSV-2 | [5 empty] | 0 | No
2027-01-02 | OSV-3 | [5 empty] | 0 | No
2027-01-02 | OSV-4 | [5 empty] | 0 | No
2027-01-02 | OSV-5 | [5 empty] | 0 | No
2027-01-02 | FSV-1 | [5 empty] | 0 | No
2027-01-03 | OSV-1 | [5 empty] | 0 | No
2027-01-03 | OSV-2 | [5 empty] | 0 | No
2027-01-03 | OSV-3 | [5 empty] | 0 | No
2027-01-03 | OSV-4 | [5 empty] | 0 | No
2027-01-03 | OSV-5 | [5 empty] | 0 | No
2027-01-03 | FSV-1 | [5 empty] | 0 | No
2027-01-04 | OSV-1 | [5 empty] | 0 | No
2027-01-04 | OSV-2 | [5 empty] | 0 | No
2027-01-04 | OSV-3 | [5 empty] | 0 | No
2027-01-04 | OSV-4 | [5 empty] | 0 | No
2027-01-04 | OSV-5 | [5 empty] | 0 | No
2027-01-04 | FSV-1 | [5 empty] | 0 | No
2027-01-05 | OSV-1 | [5 empty] | 0 | No
2027-01-05 | OSV-2 | [5 empty] | 0 | No
2027-01-05 | OSV-3 | [5 empty] | 0 | No
2027-01-05 | OSV-4 | [5 empty] | 0 | No
2027-01-05 | OSV-5 | [5 empty] | 0 | No
2027-01-05 | FSV-1 | [5 empty] | 0 | No
2027-01-06 | OSV-1 | [5 empty] | 0 | No
2027-01-06 | OSV-2 | [5 empty] | 0 | No
2027-01-06 | OSV-3 | [5 empty] | 0 | No
2027-01-06 | OSV-4 | [5 empty] | 0 | No
2027-01-06 | OSV-5 | [5 empty] | 0 | No
2027-01-06 | FSV-1 | [5 empty] | 0 | No
2027-01-07 | OSV-1 | [5 empty] | 0 | No
2027-01-07 | OSV-2 | [5 empty] | 0 | No
2027-01-07 | OSV-3 | [5 empty] | 0 | No
2027-01-07 | OSV-4 | [5 empty] | 0 | No
2027-01-07 | OSV-5 | [5 empty] | 0 | No
2027-01-07 | FSV-1 | [5 empty] | 0 | No
2027-01-08 | OSV-1 | [5 empty] | 0 | No
2027-01-08 | OSV-2 | [5 empty] | 0 | No
2027-01-08 | OSV-3 | [5 empty] | 0 | No
2027-01-08 | OSV-4 | [5 empty] | 0 | No
2027-01-08 | OSV-5 | [5 empty] | 0 | No
2027-01-08 | FSV-1 | [5 empty] | 0 | No
2027-01-09 | OSV-1 | [5 empty] | 0 | No
2027-01-09 | OSV-2 | [5 empty] | 0 | No
2027-01-09 | OSV-3 | [5 empty] | 0 | No
2027-01-09 | OSV-4 | [5 empty] | 0 | No
2027-01-09 | OSV-5 | [5 empty] | 0 | No
2027-01-09 | FSV-1 | [5 empty] | 0 | No
2027-01-10 | OSV-1 | [5 empty] | 0 | No
2027-01-10 | OSV-2 | [5 empty] | 0 | No
2027-01-10 | OSV-3 | [5 empty] | 0 | No
2027-01-10 | OSV-4 | [5 empty] | 0 | No
2027-01-10 | OSV-5 | [5 empty] | 0 | No
2027-01-10 | FSV-1 | [5 empty] | 0 | No
2027-01-11 | OSV-1 | [5 empty] | 0 | No
2027-01-11 | OSV-2 | [5 empty] | 0 | No
2027-01-11 | OSV-3 | [5 empty] | 0 | No
2027-01-11 | OSV-4 | [5 empty] | 0 | No
2027-01-11 | OSV-5 | [5 empty] | 0 | No
2027-01-11 | FSV-1 | [5 empty] | 0 | No
2027-01-12 | OSV-1 | [5 empty] | 0 | No
2027-01-12 | OSV-2 | [5 empty] | 0 | No
2027-01-12 | OSV-3 | [5 empty] | 0 | No
2027-01-12 | OSV-4 | [5 empty] | 0 | No
2027-01-12 | OSV-5 | [5 empty] | 0 | No
2027-01-12 | FSV-1 | [5 empty] | 0 | No
2027-01-13 | OSV-1 | [5 empty] | 0 | No
2027-01-13 | OSV-2 | [5 empty] | 0 | No
2027-01-13 | OSV-3 | [5 empty] | 0 | No
2027-01-13 | OSV-4 | [5 empty] | 0 | No
2027-01-13 | OSV-5 | [5 empty] | 0 | No
2027-01-13 | FSV-1 | [5 empty] | 0 | No
2027-01-14 | OSV-1 | [5 empty] | 0 | No
2027-01-14 | OSV-2 | [5 empty] | 0 | No
2027-01-14 | OSV-3 | [5 empty] | 0 | No
2027-01-14 | OSV-4 | [5 empty] | 0 | No
2027-01-14 | OSV-5 | [5 empty] | 0 | No
2027-01-14 | FSV-1 | [5 empty] | 0 | No
2027-01-15 | OSV-1 | [5 empty] | 0 | No
2027-01-15 | OSV-2 | [5 empty] | 0 | No
2027-01-15 | OSV-3 | [5 empty] | 0 | No
2027-01-15 | OSV-4 | [5 empty] | 0 | No
2027-01-15 | OSV-5 | [5 empty] | 0 | No
2027-01-15 | FSV-1 | [5 empty] | 0 | No
2027-01-16 | OSV-1 | [5 empty] | 0 | No
2027-01-16 | OSV-2 | [5 empty] | 0 | No
2027-01-16 | OSV-3 | [5 empty] | 0 | No
2027-01-16 | OSV-4 | [5 empty] | 0 | No
2027-01-16 | OSV-5 | [5 empty] | 0 | No
2027-01-16 | FSV-1 | [5 empty] | 0 | No
2027-01-17 | OSV-1 | [5 empty] | 0 | No
2027-01-17 | OSV-2 | [5 empty] | 0 | No
2027-01-17 | OSV-3 | [5 empty] | 0 | No
2027-01-17 | OSV-4 | [5 empty] | 0 | No
2027-01-17 | OSV-5 | [5 empty] | 0 | No
2027-01-17 | FSV-1 | [5 empty] | 0 | No
2027-01-18 | OSV-1 | [5 empty] | 0 | No
2027-01-18 | OSV-2 | [5 empty] | 0 | No
2027-01-18 | OSV-3 | [5 empty] | 0 | No
2027-01-18 | OSV-4 | [5 empty] | 0 | No
2027-01-18 | OSV-5 | [5 empty] | 0 | No
2027-01-18 | FSV-1 | [5 empty] | 0 | No
2027-01-19 | OSV-1 | [5 empty] | 0 | No
2027-01-19 | OSV-2 | [5 empty] | 0 | No
2027-01-19 | OSV-3 | [5 empty] | 0 | No
2027-01-19 | OSV-4 | [5 empty] | 0 | No
2027-01-19 | OSV-5 | [5 empty] | 0 | No
2027-01-19 | FSV-1 | [5 empty] | 0 | No
2027-01-20 | OSV-1 | [5 empty] | 0 | No
2027-01-20 | OSV-2 | [5 empty] | 0 | No
2027-01-20 | OSV-3 | [5 empty] | 0 | No
2027-01-20 | OSV-4 | [5 empty] | 0 | No
2027-01-20 | OSV-5 | [5 empty] | 0 | No
2027-01-20 | FSV-1 | [5 empty] | 0 | No
2027-01-21 | OSV-1 | [5 empty] | 0 | No
2027-01-21 | OSV-2 | [5 empty] | 0 | No
2027-01-21 | OSV-3 | [5 empty] | 0 | No
2027-01-21 | OSV-4 | [5 empty] | 0 | No
2027-01-21 | OSV-5 | [5 empty] | 0 | No
2027-01-21 | FSV-1 | [5 empty] | 0 | No
2027-01-22 | OSV-1 | [5 empty] | 0 | No
2027-01-22 | OSV-2 | [5 empty] | 0 | No
2027-01-22 | OSV-3 | [5 empty] | 0 | No
2027-01-22 | OSV-4 | [5 empty] | 0 | No
2027-01-22 | OSV-5 | [5 empty] | 0 | No
2027-01-22 | FSV-1 | [5 empty] | 0 | No
2027-01-23 | OSV-1 | [5 empty] | 0 | No
2027-01-23 | OSV-2 | [5 empty] | 0 | No
2027-01-23 | OSV-3 | [5 empty] | 0 | No
2027-01-23 | OSV-4 | [5 empty] | 0 | No
2027-01-23 | OSV-5 | [5 empty] | 0 | No
2027-01-23 | FSV-1 | [5 empty] | 0 | No
2027-01-24 | OSV-1 | [5 empty] | 0 | No
2027-01-24 | OSV-2 | [5 empty] | 0 | No
2027-01-24 | OSV-3 | [5 empty] | 0 | No
2027-01-24 | OSV-4 | [5 empty] | 0 | No
2027-01-24 | OSV-5 | [5 empty] | 0 | No
2027-01-24 | FSV-1 | [5 empty] | 0 | No
2027-01-25 | OSV-1 | [5 empty] | 0 | No
2027-01-25 | OSV-2 | [5 empty] | 0 | No
2027-01-25 | OSV-3 | [5 empty] | 0 | No
2027-01-25 | OSV-4 | [5 empty] | 0 | No
2027-01-25 | OSV-5 | [5 empty] | 0 | No
2027-01-25 | FSV-1 | [5 empty] | 0 | No
2027-01-26 | OSV-1 | [5 empty] | 0 | No
2027-01-26 | OSV-2 | [5 empty] | 0 | No
2027-01-26 | OSV-3 | [5 empty] | 0 | No
2027-01-26 | OSV-4 | [5 empty] | 0 | No
2027-01-26 | OSV-5 | [5 empty] | 0 | No
2027-01-26 | FSV-1 | [5 empty] | 0 | No
2027-01-27 | OSV-1 | [5 empty] | 0 | No
2027-01-27 | OSV-2 | [5 empty] | 0 | No
2027-01-27 | OSV-3 | [5 empty] | 0 | No
2027-01-27 | OSV-4 | [5 empty] | 0 | No
2027-01-27 | OSV-5 | [5 empty] | 0 | No
2027-01-27 | FSV-1 | [5 empty] | 0 | No
2027-01-28 | OSV-1 | [5 empty] | 0 | No
2027-01-28 | OSV-2 | [5 empty] | 0 | No
2027-01-28 | OSV-3 | [5 empty] | 0 | No
2027-01-28 | OSV-4 | [5 empty] | 0 | No
2027-01-28 | OSV-5 | [5 empty] | 0 | No
2027-01-28 | FSV-1 | [5 empty] | 0 | No
2027-01-29 | OSV-1 | [5 empty] | 0 | No
2027-01-29 | OSV-2 | [5 empty] | 0 | No
2027-01-29 | OSV-3 | [5 empty] | 0 | No
2027-01-29 | OSV-4 | [5 empty] | 0 | No
2027-01-29 | OSV-5 | [5 empty] | 0 | No
2027-01-29 | FSV-1 | [5 empty] | 0 | No
2027-01-30 | OSV-1 | [5 empty] | 0 | No
2027-01-30 | OSV-2 | [5 empty] | 0 | No
2027-01-30 | OSV-3 | [5 empty] | 0 | No
2027-01-30 | OSV-4 | [5 empty] | 0 | No
2027-01-30 | OSV-5 | [5 empty] | 0 | No
2027-01-30 | FSV-1 | [5 empty] | 0 | No
2027-01-31 | OSV-1 | [5 empty] | 0 | No
2027-01-31 | OSV-2 | [5 empty] | 0 | No
2027-01-31 | OSV-3 | [5 empty] | 0 | No
2027-01-31 | OSV-4 | [5 empty] | 0 | No
2027-01-31 | OSV-5 | [5 empty] | 0 | No
2027-01-31 | FSV-1 | [5 empty] | 0 | No
2027-02-01 | OSV-1 | [5 empty] | 0 | No
2027-02-01 | OSV-2 | [5 empty] | 0 | No
2027-02-01 | OSV-3 | [5 empty] | 0 | No
2027-02-01 | OSV-4 | [5 empty] | 0 | No
2027-02-01 | OSV-5 | [5 empty] | 0 | No
2027-02-01 | FSV-1 | [5 empty] | 0 | No
2027-02-02 | OSV-1 | [5 empty] | 0 | No
2027-02-02 | OSV-2 | [5 empty] | 0 | No
2027-02-02 | OSV-3 | [5 empty] | 0 | No
2027-02-02 | OSV-4 | [5 empty] | 0 | No
2027-02-02 | OSV-5 | [5 empty] | 0 | No
2027-02-02 | FSV-1 | [5 empty] | 0 | No
2027-02-03 | OSV-1 | [5 empty] | 0 | No
2027-02-03 | OSV-2 | [5 empty] | 0 | No
2027-02-03 | OSV-3 | [5 empty] | 0 | No
2027-02-03 | OSV-4 | [5 empty] | 0 | No
2027-02-03 | OSV-5 | [5 empty] | 0 | No
2027-02-03 | FSV-1 | [5 empty] | 0 | No
2027-02-04 | OSV-1 | [5 empty] | 0 | No
2027-02-04 | OSV-2 | [5 empty] | 0 | No
2027-02-04 | OSV-3 | [5 empty] | 0 | No
2027-02-04 | OSV-4 | [5 empty] | 0 | No
2027-02-04 | OSV-5 | [5 empty] | 0 | No
2027-02-04 | FSV-1 | [5 empty] | 0 | No
2027-02-05 | OSV-1 | [5 empty] | 0 | No
2027-02-05 | OSV-2 | [5 empty] | 0 | No
2027-02-05 | OSV-3 | [5 empty] | 0 | No
2027-02-05 | OSV-4 | [5 empty] | 0 | No
2027-02-05 | OSV-5 | [5 empty] | 0 | No
2027-02-05 | FSV-1 | [5 empty] | 0 | No
2027-02-06 | OSV-1 | [5 empty] | 0 | No
2027-02-06 | OSV-2 | [5 empty] | 0 | No
2027-02-06 | OSV-3 | [5 empty] | 0 | No
2027-02-06 | OSV-4 | [5 empty] | 0 | No
2027-02-06 | OSV-5 | [5 empty] | 0 | No
2027-02-06 | FSV-1 | [5 empty] | 0 | No
2027-02-07 | OSV-1 | [5 empty] | 0 | No
2027-02-07 | OSV-2 | [5 empty] | 0 | No
2027-02-07 | OSV-3 | [5 empty] | 0 | No
2027-02-07 | OSV-4 | [5 empty] | 0 | No
2027-02-07 | OSV-5 | [5 empty] | 0 | No
2027-02-07 | FSV-1 | [5 empty] | 0 | No
2027-02-08 | OSV-1 | [5 empty] | 0 | No
2027-02-08 | OSV-2 | [5 empty] | 0 | No
2027-02-08 | OSV-3 | [5 empty] | 0 | No
2027-02-08 | OSV-4 | [5 empty] | 0 | No
2027-02-08 | OSV-5 | [5 empty] | 0 | No
2027-02-08 | FSV-1 | [5 empty] | 0 | No
2027-02-09 | OSV-1 | [5 empty] | 0 | No
2027-02-09 | OSV-2 | [5 empty] | 0 | No
2027-02-09 | OSV-3 | [5 empty] | 0 | No
2027-02-09 | OSV-4 | [5 empty] | 0 | No
2027-02-09 | OSV-5 | [5 empty] | 0 | No
2027-02-09 | FSV-1 | [5 empty] | 0 | No
2027-02-10 | OSV-1 | [5 empty] | 0 | No
2027-02-10 | OSV-2 | [5 empty] | 0 | No
2027-02-10 | OSV-3 | [5 empty] | 0 | No
2027-02-10 | OSV-4 | [5 empty] | 0 | No
2027-02-10 | OSV-5 | [5 empty] | 0 | No
2027-02-10 | FSV-1 | [5 empty] | 0 | No
2027-02-11 | OSV-1 | [5 empty] | 0 | No
2027-02-11 | OSV-2 | [5 empty] | 0 | No
2027-02-11 | OSV-3 | [5 empty] | 0 | No
2027-02-11 | OSV-4 | [5 empty] | 0 | No
2027-02-11 | OSV-5 | [5 empty] | 0 | No
2027-02-11 | FSV-1 | [5 empty] | 0 | No
2027-02-12 | OSV-1 | [5 empty] | 0 | No
2027-02-12 | OSV-2 | [5 empty] | 0 | No
2027-02-12 | OSV-3 | [5 empty] | 0 | No
2027-02-12 | OSV-4 | [5 empty] | 0 | No
2027-02-12 | OSV-5 | [5 empty] | 0 | No
2027-02-12 | FSV-1 | [5 empty] | 0 | No
2027-02-13 | OSV-1 | [5 empty] | 0 | No
2027-02-13 | OSV-2 | [5 empty] | 0 | No
2027-02-13 | OSV-3 | [5 empty] | 0 | No
2027-02-13 | OSV-4 | [5 empty] | 0 | No
2027-02-13 | OSV-5 | [5 empty] | 0 | No
2027-02-13 | FSV-1 | [5 empty] | 0 | No
2027-02-14 | OSV-1 | [5 empty] | 0 | No
2027-02-14 | OSV-2 | [5 empty] | 0 | No
2027-02-14 | OSV-3 | [5 empty] | 0 | No
2027-02-14 | OSV-4 | [5 empty] | 0 | No
2027-02-14 | OSV-5 | [5 empty] | 0 | No
2027-02-14 | FSV-1 | [5 empty] | 0 | No
2027-02-15 | OSV-1 | [5 empty] | 0 | No
2027-02-15 | OSV-2 | [5 empty] | 0 | No
2027-02-15 | OSV-3 | [5 empty] | 0 | No
2027-02-15 | OSV-4 | [5 empty] | 0 | No
2027-02-15 | OSV-5 | [5 empty] | 0 | No
2027-02-15 | FSV-1 | [5 empty] | 0 | No
2027-02-16 | OSV-1 | [5 empty] | 0 | No
2027-02-16 | OSV-2 | [5 empty] | 0 | No
2027-02-16 | OSV-3 | [5 empty] | 0 | No
2027-02-16 | OSV-4 | [5 empty] | 0 | No
2027-02-16 | OSV-5 | [5 empty] | 0 | No
2027-02-16 | FSV-1 | [5 empty] | 0 | No
2027-02-17 | OSV-1 | [5 empty] | 0 | No
2027-02-17 | OSV-2 | [5 empty] | 0 | No
2027-02-17 | OSV-3 | [5 empty] | 0 | No
2027-02-17 | OSV-4 | [5 empty] | 0 | No
2027-02-17 | OSV-5 | [5 empty] | 0 | No
2027-02-17 | FSV-1 | [5 empty] | 0 | No
2027-02-18 | OSV-1 | [5 empty] | 0 | No
2027-02-18 | OSV-2 | [5 empty] | 0 | No
2027-02-18 | OSV-3 | [5 empty] | 0 | No
2027-02-18 | OSV-4 | [5 empty] | 0 | No
2027-02-18 | OSV-5 | [5 empty] | 0 | No
2027-02-18 | FSV-1 | [5 empty] | 0 | No
2027-02-19 | OSV-1 | [5 empty] | 0 | No
2027-02-19 | OSV-2 | [5 empty] | 0 | No
2027-02-19 | OSV-3 | [5 empty] | 0 | No
2027-02-19 | OSV-4 | [5 empty] | 0 | No
2027-02-19 | OSV-5 | [5 empty] | 0 | No
2027-02-19 | FSV-1 | [5 empty] | 0 | No
2027-02-20 | OSV-1 | [5 empty] | 0 | No
2027-02-20 | OSV-2 | [5 empty] | 0 | No
2027-02-20 | OSV-3 | [5 empty] | 0 | No
2027-02-20 | OSV-4 | [5 empty] | 0 | No
2027-02-20 | OSV-5 | [5 empty] | 0 | No
2027-02-20 | FSV-1 | [5 empty] | 0 | No
2027-02-21 | OSV-1 | [5 empty] | 0 | No
2027-02-21 | OSV-2 | [5 empty] | 0 | No
2027-02-21 | OSV-3 | [5 empty] | 0 | No
2027-02-21 | OSV-4 | [5 empty] | 0 | No
2027-02-21 | OSV-5 | [5 empty] | 0 | No
2027-02-21 | FSV-1 | [5 empty] | 0 | No
2027-02-22 | OSV-1 | [5 empty] | 0 | No
2027-02-22 | OSV-2 | [5 empty] | 0 | No
2027-02-22 | OSV-3 | [5 empty] | 0 | No
2027-02-22 | OSV-4 | [5 empty] | 0 | No
2027-02-22 | OSV-5 | [5 empty] | 0 | No
2027-02-22 | FSV-1 | [5 empty] | 0 | No
2027-02-23 | OSV-1 | [5 empty] | 0 | No
2027-02-23 | OSV-2 | [5 empty] | 0 | No
2027-02-23 | OSV-3 | [5 empty] | 0 | No
2027-02-23 | OSV-4 | [5 empty] | 0 | No
2027-02-23 | OSV-5 | [5 empty] | 0 | No
2027-02-23 | FSV-1 | [5 empty] | 0 | No
2027-02-24 | OSV-1 | [5 empty] | 0 | No
2027-02-24 | OSV-2 | [5 empty] | 0 | No
2027-02-24 | OSV-3 | [5 empty] | 0 | No
2027-02-24 | OSV-4 | [5 empty] | 0 | No
2027-02-24 | OSV-5 | [5 empty] | 0 | No
2027-02-24 | FSV-1 | [5 empty] | 0 | No
2027-02-25 | OSV-1 | [5 empty] | 0 | No
2027-02-25 | OSV-2 | [5 empty] | 0 | No
2027-02-25 | OSV-3 | [5 empty] | 0 | No
2027-02-25 | OSV-4 | [5 empty] | 0 | No
2027-02-25 | OSV-5 | [5 empty] | 0 | No
2027-02-25 | FSV-1 | [5 empty] | 0 | No
2027-02-26 | OSV-1 | [5 empty] | 0 | No
2027-02-26 | OSV-2 | [5 empty] | 0 | No
2027-02-26 | OSV-3 | [5 empty] | 0 | No
2027-02-26 | OSV-4 | [5 empty] | 0 | No
2027-02-26 | OSV-5 | [5 empty] | 0 | No
2027-02-26 | FSV-1 | [5 empty] | 0 | No
2027-02-27 | OSV-1 | [5 empty] | 0 | No
2027-02-27 | OSV-2 | [5 empty] | 0 | No
2027-02-27 | OSV-3 | [5 empty] | 0 | No
2027-02-27 | OSV-4 | [5 empty] | 0 | No
2027-02-27 | OSV-5 | [5 empty] | 0 | No
2027-02-27 | FSV-1 | [5 empty] | 0 | No
2027-02-28 | OSV-1 | [5 empty] | 0 | No
2027-02-28 | OSV-2 | [5 empty] | 0 | No
2027-02-28 | OSV-3 | [5 empty] | 0 | No
2027-02-28 | OSV-4 | [5 empty] | 0 | No
2027-02-28 | OSV-5 | [5 empty] | 0 | No
2027-02-28 | FSV-1 | [5 empty] | 0 | No
2027-03-01 | OSV-1 | [5 empty] | 0 | No
2027-03-01 | OSV-2 | [5 empty] | 0 | No
2027-03-01 | OSV-3 | [5 empty] | 0 | No
2027-03-01 | OSV-4 | [5 empty] | 0 | No
2027-03-01 | OSV-5 | [5 empty] | 0 | No
2027-03-01 | FSV-1 | [5 empty] | 0 | No
2027-03-02 | OSV-1 | [5 empty] | 0 | No
2027-03-02 | OSV-2 | [5 empty] | 0 | No
2027-03-02 | OSV-3 | [5 empty] | 0 | No
2027-03-02 | OSV-4 | [5 empty] | 0 | No
2027-03-02 | OSV-5 | [5 empty] | 0 | No
2027-03-02 | FSV-1 | [5 empty] | 0 | No
2027-03-03 | OSV-1 | [5 empty] | 0 | No
2027-03-03 | OSV-2 | [5 empty] | 0 | No
2027-03-03 | OSV-3 | [5 empty] | 0 | No
2027-03-03 | OSV-4 | [5 empty] | 0 | No
2027-03-03 | OSV-5 | [5 empty] | 0 | No
2027-03-03 | FSV-1 | [5 empty] | 0 | No
2027-03-04 | OSV-1 | [5 empty] | 0 | No
2027-03-04 | OSV-2 | [5 empty] | 0 | No
2027-03-04 | OSV-3 | [5 empty] | 0 | No
2027-03-04 | OSV-4 | [5 empty] | 0 | No
2027-03-04 | OSV-5 | [5 empty] | 0 | No
2027-03-04 | FSV-1 | [5 empty] | 0 | No
2027-03-05 | OSV-1 | [5 empty] | 0 | No
2027-03-05 | OSV-2 | [5 empty] | 0 | No
2027-03-05 | OSV-3 | [5 empty] | 0 | No
2027-03-05 | OSV-4 | [5 empty] | 0 | No
2027-03-05 | OSV-5 | [5 empty] | 0 | No
2027-03-05 | FSV-1 | [5 empty] | 0 | No
2027-03-06 | OSV-1 | [5 empty] | 0 | No
2027-03-06 | OSV-2 | [5 empty] | 0 | No
2027-03-06 | OSV-3 | [5 empty] | 0 | No
2027-03-06 | OSV-4 | [5 empty] | 0 | No
2027-03-06 | OSV-5 | [5 empty] | 0 | No
2027-03-06 | FSV-1 | [5 empty] | 0 | No
2027-03-07 | OSV-1 | [5 empty] | 0 | No
2027-03-07 | OSV-2 | [5 empty] | 0 | No
2027-03-07 | OSV-3 | [5 empty] | 0 | No
2027-03-07 | OSV-4 | [5 empty] | 0 | No
2027-03-07 | OSV-5 | [5 empty] | 0 | No
2027-03-07 | FSV-1 | [5 empty] | 0 | No
2027-03-08 | OSV-1 | [5 empty] | 0 | No
2027-03-08 | OSV-2 | [5 empty] | 0 | No
2027-03-08 | OSV-3 | [5 empty] | 0 | No
2027-03-08 | OSV-4 | [5 empty] | 0 | No
2027-03-08 | OSV-5 | [5 empty] | 0 | No
2027-03-08 | FSV-1 | [5 empty] | 0 | No
2027-03-09 | OSV-1 | [5 empty] | 0 | No
2027-03-09 | OSV-2 | [5 empty] | 0 | No
2027-03-09 | OSV-3 | [5 empty] | 0 | No
2027-03-09 | OSV-4 | [5 empty] | 0 | No
2027-03-09 | OSV-5 | [5 empty] | 0 | No
2027-03-09 | FSV-1 | [5 empty] | 0 | No
2027-03-10 | OSV-1 | [5 empty] | 0 | No
2027-03-10 | OSV-2 | [5 empty] | 0 | No
2027-03-10 | OSV-3 | [5 empty] | 0 | No
2027-03-10 | OSV-4 | [5 empty] | 0 | No
2027-03-10 | OSV-5 | [5 empty] | 0 | No
2027-03-10 | FSV-1 | [5 empty] | 0 | No
2027-03-11 | OSV-1 | [5 empty] | 0 | No
2027-03-11 | OSV-2 | [5 empty] | 0 | No
2027-03-11 | OSV-3 | [5 empty] | 0 | No
2027-03-11 | OSV-4 | [5 empty] | 0 | No
2027-03-11 | OSV-5 | [5 empty] | 0 | No
2027-03-11 | FSV-1 | [5 empty] | 0 | No
2027-03-12 | OSV-1 | [5 empty] | 0 | No
2027-03-12 | OSV-2 | [5 empty] | 0 | No
2027-03-12 | OSV-3 | [5 empty] | 0 | No
2027-03-12 | OSV-4 | [5 empty] | 0 | No
2027-03-12 | OSV-5 | [5 empty] | 0 | No
2027-03-12 | FSV-1 | [5 empty] | 0 | No
2027-03-13 | OSV-1 | [5 empty] | 0 | No
2027-03-13 | OSV-2 | [5 empty] | 0 | No
2027-03-13 | OSV-3 | [5 empty] | 0 | No
2027-03-13 | OSV-4 | [5 empty] | 0 | No
2027-03-13 | OSV-5 | [5 empty] | 0 | No
2027-03-13 | FSV-1 | [5 empty] | 0 | No
2027-03-14 | OSV-1 | [5 empty] | 0 | No
2027-03-14 | OSV-2 | [5 empty] | 0 | No
2027-03-14 | OSV-3 | [5 empty] | 0 | No
2027-03-14 | OSV-4 | [5 empty] | 0 | No
2027-03-14 | OSV-5 | [5 empty] | 0 | No
2027-03-14 | FSV-1 | [5 empty] | 0 | No
2027-03-15 | OSV-1 | [5 empty] | 0 | No
2027-03-15 | OSV-2 | [5 empty] | 0 | No
2027-03-15 | OSV-3 | [5 empty] | 0 | No
2027-03-15 | OSV-4 | [5 empty] | 0 | No
2027-03-15 | OSV-5 | [5 empty] | 0 | No
2027-03-15 | FSV-1 | [5 empty] | 0 | No
2027-03-16 | OSV-1 | [5 empty] | 0 | No
2027-03-16 | OSV-2 | [5 empty] | 0 | No
2027-03-16 | OSV-3 | [5 empty] | 0 | No
2027-03-16 | OSV-4 | [5 empty] | 0 | No
2027-03-16 | OSV-5 | [5 empty] | 0 | No
2027-03-16 | FSV-1 | [5 empty] | 0 | No
2027-03-17 | OSV-1 | [5 empty] | 0 | No
2027-03-17 | OSV-2 | [5 empty] | 0 | No
2027-03-17 | OSV-3 | [5 empty] | 0 | No
2027-03-17 | OSV-4 | [5 empty] | 0 | No
2027-03-17 | OSV-5 | [5 empty] | 0 | No
2027-03-17 | FSV-1 | [5 empty] | 0 | No
2027-03-18 | OSV-1 | [5 empty] | 0 | No
2027-03-18 | OSV-2 | [5 empty] | 0 | No
2027-03-18 | OSV-3 | [5 empty] | 0 | No
2027-03-18 | OSV-4 | [5 empty] | 0 | No
2027-03-18 | OSV-5 | [5 empty] | 0 | No
2027-03-18 | FSV-1 | [5 empty] | 0 | No
2027-03-19 | OSV-1 | [5 empty] | 0 | No
2027-03-19 | OSV-2 | [5 empty] | 0 | No
2027-03-19 | OSV-3 | [5 empty] | 0 | No
2027-03-19 | OSV-4 | [5 empty] | 0 | No
2027-03-19 | OSV-5 | [5 empty] | 0 | No
2027-03-19 | FSV-1 | [5 empty] | 0 | No

## Cargo Manifest
CARGO MANIFEST & TRACKING
Item # | Cargo Description | Quantity | Unit | Supplier | Required Date | Vessel Assigned | Status
1 | Rheguard SBM (16.3 PPG) | 6,000 | bbls | SLB | 2026-12-21 | OSV-1 | Planned
2 | DIPRO (16.3 PPG) | 7,000 | bbls | SLB | 2026-12-21 | OSV-1 | Planned
3 | DIPRO PRE-MIX (16.3 PPG) | 3,000 | bbls | SLB | 2026-12-21 | OSV-1 | Planned
4 | DIPRO DIF Solids Free (16.5 PPG) | 350 | bbls | SLB | 2026-12-21 | OSV-1 | Planned
5 | CaBr2/ZnBr2 (16.5-17.1#) | 8,500-10,000 | bbls | Tetra | 2026-12-21 | OSV-2 | Planned
6 | CaBr2 Spacer Brine (14.2#) | 700 | bbls | Tetra | 2026-12-21 | OSV-2 | Planned
7 | CaBr2/ZnBr2 Spike (19.2#) | 276 | bbls | Tetra | 2027-01-05 | OSV-2 | Planned
8 | NaBr Packer Fluid (12.4#) | 5,500 | bbls | Tetra | 2027-01-15 | OSV-2 | Planned
9 | CaBr2 in 25-bbl MPTs (14.2#) | 46 | bbls (2 MPTs) | Tetra | 2027-01-15 | OSV-3 | Planned
10 | NaBr in 25-bbl MPTs (12.4#) | 46 | bbls (2 MPTs) | Tetra | 2027-01-20 | OSV-3 | Planned
11 | NaBr in 350-gal tote (12.4#) | 3 | bbls (1 tote) | Tetra | 2027-01-20 | OSV-3 | Planned
12 | CaBr2/ZnBr2 in 25-bbl MPTs | 276 | bbls (12 MPTs) | Tetra | 2027-01-10 | OSV-3 | Planned
13 | 9⅝" Drill Pipe V150 | 4,357 | feet | Stena/Workstrings | 2026-12-20 | OSV-3 | Planned
14 | 5½" Drill Pipe V150 Delta576 | 7,900 | feet | Stena/Workstrings | 2026-12-20 | OSV-3 | Planned
15 | 4½" Drill Pipe V150 Delta425 (20 lb/ft) | 5,000 | feet | Stena/Workstrings | 2026-12-23 | OSV-3 | Planned
16 | 4½" Drill Pipe V150 Delta425 (16.6 lb/ft) | 18,000 | feet | Stena/Workstrings | 2026-12-27 | OSV-3 | Planned