## Slide 1
Sparta EV Run Strategy
Supporting Sparta demand while minimizing logistics operating cost
Prepared for: Logistics Delivery Manager

## Slide 2
Decision to Make
Select the most practical EV run strategy to support Sparta demand.
Minimize logistics operating cost while preserving execution reliability.
Prefer an existing-fleet solution over adding a dedicated OSV.
Speaker notes: This decision is about finding the best operating model for Sparta without structurally increasing cost unless reliability demands it.

## Slide 3
Business Context
Sparta introduces new diesel and logistics demand into the EV run system.
FSV all-in run cost is about $25k/day.
OSV all-in run cost is about $80k/day.
Objective: absorb demand with the current fleet wherever feasible.
Speaker notes: The cost gap between FSV and OSV is the key economic driver. Any solution that adds a permanent OSV must provide a clear reliability benefit to justify the spend.

## Slide 4
Options Evaluated
Current State: baseline only, does not support Sparta demand.
Option 1: 12-month solution with added OSV; Mars EV dates shift.
Option 2: no asset moved off current EV schedule.
Option 3: best fit for about 8 months; higher weather recovery risk.
Speaker notes: The analysis compares cost, fleet saturation, and schedule recoverability. The main question is where to trade off cost versus resilience.

## Slide 5
Executive Recommendation
Use Option 3 as the base strategy during stable operating months.
Keep Option 1 as the contingency for fronts season or repeat recovery failures.
Do not pursue Option 2.
Speaker notes: Option 3 is the lowest-cost workable plan. Option 1 remains the lowest-risk backup if weather or recovery performance degrades.

## Slide 6
Option Comparison
Option | Pros | Cons | Takeaway
Current State | Established operating rhythm. Existing vessel pattern is familiar. | Does not support Sparta demand. | Baseline only.
Option 1 | Most stable operating model. Dedicated OSV for Sparta. Only Mars requires EV date change. Better recovery after delays. | Highest cost due to added OSV. Does not meet the goal of using the existing fleet. | Best reliability, weakest cost efficiency.
Option 2 | Keeps current EV dates unchanged. | Overcommits FSV capacity. Too many vessels committed at once. Limited recovery flexibility. | Not recommended.
Option 3 | Best cost and operability balance for most of the year. Avoids full-time added OSV. Keeps fleet count closer to current state. | Tighter recovery margin. Higher exposure to fronts and weather disruption. | Best base strategy if paired with clear contingency triggers.
Speaker notes: This is the core decision slide. If leadership wants the lowest cost, Option 3 is the answer. If leadership wants the most conservative 12-month operating plan, Option 1 is the answer.

## Slide 7
Why Option 1 Works
Cleanest operational setup.
Sparta demand is separated onto a dedicated OSV.
Lower schedule congestion and easier recovery after disruption.
Only Mars requires an EV date adjustment.
Speaker notes: Option 1 reduces operational complexity by absorbing Sparta with dedicated capacity. The tradeoff is straightforward: reliability improves, but cost increases materially.

## Slide 8
Why Option 2 Falls Out
Keeps all current EV dates unchanged.
Pulls too many FSVs out of the system at the same time.
Leaves too little flexibility to recover after delays.
Creates the highest fleet saturation of the options reviewed.
Speaker notes: Option 2 protects schedule dates, but it does so by consuming too much fleet flexibility. That makes it operationally fragile and not suitable for execution.

## Slide 9
Why Option 3 Is Preferred
Lowest-cost workable strategy.
Maintains a 5-vessel pattern instead of expanding to 6 vessels.
Supports Sparta without committing to a full-time added OSV.
Best fit during normal weather months.
Speaker notes: Option 3 is preferred because it preserves cost discipline while still making the schedule work. Its weakness is not day-to-day execution in stable conditions, but recovery when fronts begin to disrupt the cycle.

## Slide 10
Key Risk in Option 3
Recovery windows become tighter once fronts begin.
Existing vessels absorb more of the workload.
A missed run can cascade more easily into the next cycle.
Sparta, Auger, and ESA rotation becomes more sensitive to disruption.
Speaker notes: The right way to present Option 3 is not as a perfect year-round solution. It is the best base plan, but it needs a defined escalation path once weather risk rises.

## Slide 11
Proposed Trigger Points
One missed Sparta fuel or diesel delivery window.
Two consecutive weather-driven EV schedule slips.
Failure to recover Glenn or the swing FSV back to planned port timing within one cycle.
Repeated weather disruption affecting Sparta, Auger, or ESA rotation.
Speaker notes: These triggers give management a clear operational threshold for when the cost of supplemental OSV support becomes justified.

## Slide 12
Recommended Decision Statement
Approve Option 3 as the primary Sparta support strategy during stable months.
Pre-align on supplemental OSV support during fronts season or if trigger conditions are met.
Reject Option 2 as a non-viable operating plan.
Speaker notes: This closes the discussion with a practical recommendation: preserve cost discipline by default, but do not wait too long to escalate if reliability begins to slip.

## Slide 13
Closing Message
Option 3 is the best base strategy.
Option 1 is the best contingency strategy.
The decision should be made now with trigger-based escalation agreed in advance.
Speaker notes: This is the balanced message for leadership: lowest-cost execution with a clear backup plan, rather than choosing between cost and reliability as if they are mutually exclusive.