## OSV Demand Tracker
Status | Asset | Project | Activity | Base Delivery Date | Offshore Req Date | Offloading Complete Date | Estimated Duration (hrs.) | Back to Port | Transit Time Back to Port
Complete | Pontus | Sparta 007 Drill Pilot Hole - | GL 01 OSV / 48 hrs / 15,000 bbl of WBM, Cement, WBM Pallet Chemicals, 1,500 Sacks of Gel, Sparta 8-1/2" BHA, Cement Head **MEET AT GB959** | 2026-01-28 | 2026-01-30 20:00 | 2026-02-01 20:00 | 48 | 2026-02-02 16:00 | 20
Complete | Pontus | Sparta 008 Drill Pilot Hole | GL 01a OSV / 12 hrs / 2,500 bbl of 16 ppg WBM (BBL COULD INCREASE) | 2026-02-01 | 2026-02-04 01:30 | 2026-02-04 13:30 | 12 | 2026-02-05 09:30 | 20
Complete | Pontus | Llano LL003 Abandonment | GL 01 OSV / 24 hours / Millout BHA, BOP Test Tools, LDS Recovery Tools, 4-1/2" DP | 2026-02-12 | 2026-02-15 18:00 | 2026-02-16 18:00 | 24 | 2026-02-17 12:00 | 18
Complete | Pontus | Llano LL003 Abandonment | GL 01a OSV / 12 hrs / Loadmaster Container, Perdido Fluid Transfer | 2026-02-17 | 2026-02-18 | 2026-02-19 12:00 | 36 | 2026-02-20 06:00 | 18
Complete | Pontus | Llano LL003 Abandonment | GL 03 OSV / 24 hrs / 7-3/4" CIBP, MI Pallet Chemicals & Barite GL 06 OSV / 36 hrs / 13-5/8" Casing Tools, WBCO BHA, 16" CIBP, 22" Plug, Backload 13-5/8" Casing | 2026-02-19 | 2026-02-23 04:00 | 2026-02-24 16:00 | 36 | 2026-02-25 10:00 | 18
Complete | Pontus | Llano LL003 Abandonment | GL 04 OSV / 36 hours / SBM Chemicals, 10-3/4" Casing Tools, ASA Tools, Backload 10-3/4" Casing | 2026-02-23 | 2026-02-26 11:15 | 2026-02-27 23:15 | 36 | 2026-02-28 17:15 | 18
Complete | Pontus | Llano LL003 Abandonment | GL 06 OSV / 36 hrs / 13-5/8" Casing Tools, WBCO BHA, 16" CIBP, 22" Plug, Backload 13-5/8" Casing | 2026-02-26 | 2026-03-01 09:00 | 2026-03-02 21:00 | 36 | 2026-03-03 15:00 | 18
Complete | Pontus | Stones 20 Top Hole | GL 01 OSV / 36 hrs / 10,000 bbl of 16 ppg WBM, WBM Chemicals, 38" Jet Pipe, 28" Casing, Jetting / 32" BHA, LPWHH, Casing Tools | 2026-03-03 | 2026-03-05 18:00 | 2026-03-07 06:00 | 36 | 2026-03-08 02:00 | 20
Complete | Pontus | Stones 20 Top Hole | GL 02 OSV / 36 hrs / 14,000 bbl of 16 ppg WBM, 26" BHA, 28" Casing Tools, 28" Backups | 2026-03-06 | 2026-03-09 20:45 | 2026-03-11 08:45 | 36 | 2026-03-12 04:45 | 20
Complete | Pontus | Stones 20 Top Hole | GL 03 OSV / 24 hrs / 22" Casing, 22" Casing Tools, 22" Backups | 2026-03-09 | 2026-03-12 18:45 | 2026-03-13 18:45 | 24 | 2026-03-14 14:45 | 20
Complete | Pontus | Dover 2 ST01BP01 | GL 01 OSV / 36 hrs / Weekly Groceries & Rig Supplies, SPM, Umbilical, Spooler **MEET RIG AT WR508** | 2026-03-17 | 2026-03-19 22:00 | 2026-03-21 10:00 | 36 | 2026-03-22 04:00 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 02 OSV / 36 hrs/ SBM Chemicals / 9-3/8" Casing **MEET at Grand Isle 061** | 2026-03-24 | 2026-03-26 04:00 | 2026-03-27 16:00 | 36 | 2026-03-28 10:00 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 03 OSV / 24hrs / SBM/ THS and WH Adapter / Cleanout BHA / Drill Pipe/ Cement *Meet at GI061* | 2026-03-27 | 2026-03-29 12:00 | 2026-03-30 12:00 | 24 | 2026-03-31 06:00 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 07 OSV / 36 hrs / 9-7/8" x 11" Drill Ahead BHA, 9-3/8" / NXT / Background Pallet Chemicals | 2026-04-13 | 2026-04-15 03:00 | 2026-04-16 15:00 | 36 | 2026-04-17 09:00 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 09 OSV/ 36 hrs / 8-5/8" x 7-3/4" liner and Casing Tools -- Backload 9-7/8" x 11" BHA / 9-3/8" Pipe, Hanger Basket, Casing Tools and Accessories | 2026-04-26 | 2026-04-28 18:00 | 2026-04-30 06:00 | 36 | 2026-05-01 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 11 OSV / 36 hrs / Weekly Groceries & Rig Supplies--Backload 4,000bbls of 13.1# SBM | 2026-04-29 | 2026-05-01 06:00 | 2026-05-02 18:00 | 36 | 2026-05-03 12:00 | 18
Complete | Pontus | Dover 2 ST01BP01 | GL 13 OSV / 16 hrs / Drill Water & **Primary Function to Backload 6,000 bbls SBM for Well Displacement** | 2026-05-13 | 2026-05-14 | 2026-05-14 16:00 | 16 | 2026-05-15 10:00 | 18
Complete | Pontus | Dover 002 Completion | GL 01 OSV / 36 hrs / 9,000 bb of 14.4 ppg Brine, Brine Chemicals, Completion DP, Filtration, WBCO, HPDU, HPDU Iron | 2026-05-11 | 2026-05-13 18:00 | 2026-05-15 06:00 | 36 | 2026-05-16 | 18
Complete | Poseidon | Whale 8 Completion | GL 01a OSV / 48hrs - WBCO / HPDU / 3" Iron (HPDU) | 2026-01-24 | 2026-01-26 05:12 | 2026-01-28 05:12 | 48 | 2026-01-30 05:12 | 48
Complete | Poseidon | Whale 8 Completion | GL 02 OSV / 36hrs - SLB TCP / Supreme TCP Iron/Head / HES Deburr | 2026-01-31 | 2026-02-04 06:00 | 2026-02-05 18:00 | 36 | 2026-02-07 18:00 | 48
Complete | Poseidon | Whale 8 Completion | GL 04 OSV / 24hrs - MST and Frac Equipment | 2026-02-04 | 2026-02-08 01:30 | 2026-02-09 01:30 | 24 | 2026-02-11 01:30 | 48
Complete | Poseidon | Whale 8 Completion | GL 06 OSV- THS and TA Equipment, FLDCO Equipment **VESSEL NEEDS TO HAVE BRINE TANKS** | 2026-02-19 | 2026-02-22 06:00 | 2026-02-23 06:00 | 24 | 2026-02-25 06:00 | 48
Complete | Poseidon | Whale 8 Completion | GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment / Packer Fluid | 2026-02-24 | 2026-02-26 12:00 | 2026-02-28 12:00 | 48 | 2026-03-02 12:00 | 48
Complete | Poseidon | Whale 8 Completion | GL 10 OSV / 48hrs - Power Wire / SSXT | 2026-03-15 | 2026-03-18 05:00 | 2026-03-20 05:00 | 48 | 2026-03-22 05:00 | 48
Complete | Poseidon | Whale 8 Completion | GL 11 OSV / 48hrs: THS (LWX9) SBM / Base Oil- Backload Completions Equipment | 2026-03-19 | 2026-03-23 06:45 | 2026-03-24 06:45 | 24 | 2026-03-26 06:45 | 48
Complete | Poseidon | Whale 9 Completion | GL 01 OSV / 72hrs - Brine / DE / WBCO | 2026-03-27 | 2026-03-29 23:59 | 2026-04-01 23:59 | 72 | 2026-04-03 23:59 | 48
Complete | Poseidon | Whale 9 Completion | GL 03 OSV / 36hrs - SLB TCP / Supreme TCP Iron/Head / HES Deburr | 2026-04-06 | 2026-04-08 22:00 | 2026-04-10 10:00 | 36 | 2026-04-12 10:00 | 48
Complete | Poseidon | Whale 9 Completion | GL 03a OSV / 4hrs: Shared run w/ Perdido for HES Debris Tank | 2026-04-08 | 2026-04-09 23:00 | 2026-04-10 03:00 | 4 | 2026-04-12 03:00 | 48
Complete | Poseidon | Whale 9 Completion | GL 04 OSV / 48hrs - MST / Frac Equipment / CaCl2 | 2026-04-13 | 2026-04-15 12:00 | 2026-04-16 12:00 | 24 | 2026-04-18 12:00 | 48
Complete | Poseidon | Whale 9 Completion | GL 04b OSV / 24hrs: Shared Vessel for MST Equipment | 2026-04-13 | 2026-04-16 02:00 | 2026-04-17 02:00 | 24 | 2026-04-19 02:00 | 48
Complete | Poseidon | Whale 9 Completion | GL 05 HOS Carolina / 120hrs - Frac Heads & THS | 2026-04-16 | 2026-04-19 13:45 | 2026-04-24 13:45 | 120 | 2026-04-26 13:45 | 48
Complete | Poseidon | Whale 9 Completion | GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment / Packer Fluid GL 09 OSV / 48hrs - ROCS / Upper Completions Equipment | 2026-04-26 | 2026-04-29 06:15 | 2026-05-01 06:15 | 48 | 2026-05-03 06:15 | 48
Complete | Poseidon | Whale 9 Completion | GL 10 OSV / 48hrs- Power Wire / SSXT | 2026-04-30 | 2026-05-03 06:15 | 2026-05-05 06:15 | 48 | 2026-05-07 06:15 | 48
Complete | Poseidon | Whale 10 Deepening | GL 01 OSV / 72 HRS: Post Spud Equipment / 14 CSG / 22" Stormpacker / SBM / Barite / Base Oil | 2026-05-08 | 2026-05-10 07:00 | 2026-05-13 07:00 | 72 | 2026-05-15 07:00 | 48
Complete | Poseidon | Whale 10 Deepening | GL 02 OSV / 48 HRS: 18.125" BHA / Cutting Boxes / Liner Hanger / Cement | 2026-05-14 | 2026-05-16 06:00 | 2026-05-18 06:00 | 48 | 2026-05-20 06:00 | 48
Complete | Poseidon | Whale 10 Deepening | GL 03 OSV / 72 HRS: 12.25" BHA / 9 5/8" Liner / Run Equipment | 2026-05-25 | 2026-05-27 13:00 | 2026-05-29 13:00 | 48 | 2026-05-31 13:00 | 48
Complete | Poseidon | Whale 10 Deepening | GL 03a OSV / 48 hrs: Groceries / Resupply / GTM-69 DP | 2026-05-25 | 2026-05-27 06:00 | 2026-05-29 06:00 | 48 | 2026-05-31 06:00 | 48
Planned | Poseidon | Whale 10 Deepening | GL 04 OSV / 48 HRS: Tieback / Liner Hanger / Run Equipment / Cement | 2026-06-23 | 2026-06-25 05:15 | 2026-06-27 05:15 | 48 | 2026-06-29 05:15 | 48
Planned | Poseidon | Whale 10 Deepening | GL 04a OSV (Shared) / 6 hrs: Class H CMT | 2026-06-09 | 2026-06-12 | 2026-06-12 06:00 | 6 | 2026-06-14 06:00 | 48
Planned | Poseidon | Whale 10 Deepening | GL 03 OSV / 72 HRS: 12.25" BHA / 9 5/8" Liner / Run Equipment | 2026-06-20 | 2026-06-22 12:30 | 2026-06-25 12:30 | 72 | 2026-06-27 12:30 | 48
Planned | Poseidon | Whale 10 Deepening | GL 04d OSV / 24 HRS: 14.5"x16.5" BHA / SBM | 2026-06-13 | 2026-06-16 12:00 | 2026-06-17 12:00 | 24 | 2026-06-19 12:00 | 48
Planned | Poseidon | Whale 10 Completion | GL 01 OSV / 72hrs - Brine / DE / WBCO / THS | 2026-07-03 | 2026-07-06 16:30 | 2026-07-09 16:30 | 72 | 2026-07-11 16:30 | 48
Planned | Poseidon | Whale 10 Completion | GL 02 OSV-WBCO / HPDU / 3" Iron / Tetra Filtration | 2026-07-06 | 2026-07-09 07:45 | 2026-07-11 07:45 | 48 | 2026-07-13 07:45 | 48
Planned | Poseidon | Whale 10 Completion | GL 04 OSV- SLB TCP / Supreme TCP Iron/Head / HES Deburr / Brine | 2026-07-12 | 2026-07-15 22:45 | 2026-07-18 22:45 | 72 | 2026-07-20 22:45 | 48
Planned | Poseidon | Whale 10 Completion | GL 05 OSV- MST / Frac Equipment | 2026-07-16 | 2026-07-20 14:30 | 2026-07-21 14:30 | 24 | 2026-07-23 14:30 | 48
Planned | Poseidon | Whale 10 Completion | GL 06 HOS Carolina / 120 hrs - Frac Heads | 2026-07-22 | 2026-07-25 07:15 | 2026-07-30 07:15 | 120 | 2026-08-01 07:15 | 48
Planned | Poseidon | Whale 10 Completion | GL 07 OSV- ROCS / Upper Completions Equipment / Packer Fluid | 2026-07-25 | 2026-07-28 07:15 | 2026-07-30 07:15 | 48 | 2026-08-01 07:15 | 48
Planned | Poseidon | Whale 10 Completion | GL 08 OSV/FSV- Power Wire / Tree | 2026-07-29 | 2026-08-01 07:15 | 2026-08-03 07:15 | 48 | 2026-08-05 07:15 | 48
Complete | Proteus | VX004 Deepen | GL 01 OSV - SBM 16" Casing, RB Tools, CMT, Barite, FMC Tools | 2026-01-24 | 2026-01-26 13:15 | 2026-01-27 13:15 | 24 | 2026-01-28 05:15 | 16
Complete | Proteus | VX004 Deepen | GL 02a OSV - Contigency 18" String, 18" Run Tools | 2026-01-30 | 2026-01-31 00:30 | 2026-02-01 00:30 | 24 | 2026-02-01 16:30 | 16
Complete | Proteus | VX004 Deepen | GL 04 OSV - 14-3/4" BHA, 12-1/4" Casing & RB Tools, Centralizers, SBM | 2026-01-31 | 2026-02-02 04:15 | 2026-02-03 04:15 | 24 | 2026-02-03 20:15 | 16
Complete | Proteus | VX004 Deepen | GL 05 OSV - 12/1/4" Hanger, 12-1/4" Run Toos, RTTS, Cement Head / Swage | 2026-02-04 | 2026-02-06 17:00 | 2026-02-07 17:00 | 24 | 2026-02-08 09:00 | 16
Complete | Proteus | VX004 Deepen | GL 06a OSV - Tri-State, 8-5/8" Casing, RB Tools, SBM, Barite, CMT | 2026-02-09 | 2026-02-12 | 2026-02-13 | 24 | 2026-02-13 16:00 | 16
Complete | Proteus | VX004 Deepen | GL 07 OSV - 8-5/8" Hanger, 8-5/8" Run Tools, THS & Tools | 2026-02-15 | 2026-02-16 14:00 | 2026-02-17 14:00 | 24 | 2026-02-18 06:00 | 16
Complete | Proteus | VX004 Deepen | GL 08 OSV - Backload SBM, DP, Metrology | 2026-02-19 | 2026-02-22 01:15 | 2026-02-23 01:15 | 24 | 2026-02-23 17:15 | 16
Complete | Proteus | VX004 Deepen | GL 09 OSV - WBCO BHA, DIF, Rig Chem, Tubing | 2026-02-21 | 2026-02-23 19:15 | 2026-02-24 19:15 | 24 | 2026-02-25 11:15 | 16
Complete | Proteus | VX004 Deepen | GL 10 OSV - SBM Backload, 6-3/4" BHA | 2026-02-26 | 2026-02-28 10:45 | 2026-03-01 10:45 | 24 | 2026-03-02 02:45 | 16
Complete | Proteus | VX004 Deepen | GL 11 OSV - Brine, HPDU, Filtration, GT-M69 | 2026-02-28 | 2026-03-01 12:45 | 2026-03-02 12:45 | 24 | 2026-03-03 04:45 | 16
Complete | Proteus | VX004 Completion | GL 01 OSV - Lower Completion Tools | 2026-03-03 | 2026-03-05 17:15 | 2026-03-06 17:15 | 24 | 2026-03-07 09:15 | 16
Complete | Proteus | VX004 Completion | GL 02 OSV - WBCU & WBRR BHAs / DIF Backload | 2026-03-08 | 2026-03-11 16:30 | 2026-03-12 16:30 | 24 | 2026-03-13 08:30 | 16
Complete | Proteus | VX004 Completion | GL 03 OSV - Upper Completion Tools (Packer Fluid) | 2026-03-11 | 2026-03-14 20:00 | 2026-03-15 20:00 | 24 | 2026-03-16 12:00 | 16
Complete | Proteus | VX004 Completion | GL 05 OSV - Tree / Backload (B/H CaBr & NaBr) | 2026-03-18 | 2026-03-20 04:30 | 2026-03-21 04:30 | 24 | 2026-03-21 20:30 | 16
Complete | Proteus | VX004 Completion | GL 06 OSV - Backload Completion Equipment | 2026-03-22 | 2026-03-24 16:30 | 2026-03-25 16:30 | 24 | 2026-03-26 08:30 | 16
Complete | Proteus | DEMOB | GL 01 OSV - Backload CML/ROV/DP | 2026-03-28 | 2026-03-30 | 2026-03-31 | 24 | 2026-03-31 03:00 | 3
Complete | Proteus | DEMOB | GL 02 OSV - Backload Riser | 2026-03-31 | 2026-04-01 04:00 | 2026-04-02 04:00 | 24 | 2026-04-02 07:00 | 3
Complete | Stena Evolution | Sparta SP203 Deepening | GL 09e OSV - 30 Hours -6k bbls 16.3 PPG SBM/ 5000k SXS Barite / Misc. | 2026-01-23 | 2026-01-27 06:00 | 2026-01-28 18:00 | 36 | 2026-01-29 13:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 09g OSV - 60 Hours -Backload Casing/ Demob Vessel / Backload SBM | 2026-02-07 | 2026-02-09 06:00 | 2026-02-11 06:00 | 48 | 2026-02-12 01:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10 OSV - 36 Hours - Wireline Equipment / Bridge Plug / Pipe Racks Excess 10.50" & 11.25" Casing / B/L SBM?? | 2026-02-15 | 2026-02-18 06:48 | 2026-02-19 18:48 | 36 | 2026-02-20 13:48 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10b OSV- 12 Hours - Class H Cement Blend (Sparta Specific) | 2026-01-30 | 2026-02-02 02:00 | 2026-02-02 14:00 | 12 | 2026-02-03 09:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10c OSV- 24 Hours- 6K bbls SBM / 4k sxs Barite | 2026-02-02 | 2026-02-03 06:00 | 2026-02-04 06:00 | 24 | 2026-02-05 01:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10e OSV- 24 Hours- Groceries / Rig Supplies / 6-5/8" DP (60 Jnts) | 2026-02-06 | 2026-02-07 07:00 | 2026-02-08 07:00 | 24 | 2026-02-09 02:00 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 10f OSV - 30 Hours - THS Install / Misc. GL 11 OSV - 30 Hours - THS Install / Misc. | 2026-02-19 | 2026-02-21 11:30 | 2026-02-22 17:30 | 30 | 2026-02-23 12:30 | 19
Complete | Stena Evolution | Sparta SP203 Deepening | GL 12 OSV - 50 Hours - Demob / Backload SBM / RCS Pit Cleaning Equipment/Backload DP | 2026-02-20 | 2026-02-22 11:30 | 2026-02-24 13:30 | 50 | 2026-02-25 08:30 | 19
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 01 OSV 60 Hours - 38", 32", / 32" & 29" BHA/ LPWHH FMC Equip. | 2026-02-12 | 2026-02-15 03:48 | 2026-02-17 15:48 | 60 | 2026-02-18 00:48 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 02 OSV- 50 Hours - 28" Casing/ WBM/ FOAM Equipment/16 PPG WBM/ Class H Cmt | 2026-02-13 | 2026-02-16 21:54 | 2026-02-18 23:54 | 50 | 2026-02-19 08:54 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 03 OSV 60 Hours - 22" Casing 26"x28" BHA / WBM / Cement / Pallet Material | 2026-02-16 | 2026-02-19 19:30 | 2026-02-22 07:30 | 60 | 2026-02-22 16:30 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 03b OSV - 24 Hours - 10k-12k WBM / Groceries / Rig Supplies GL 03a OSV - 24 Hours - 10k-12k WBM | 2026-02-17 | 2026-02-20 06:15 | 2026-02-21 06:15 | 24 | 2026-02-21 15:15 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 04 OSV - 48 Hours - 10k-12-k WBM / Class H Cement | 2026-02-18 | 2026-02-21 12:15 | 2026-02-23 12:15 | 48 | 2026-02-23 21:15 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 05 OSV - 60 Hours - 18" Casing / 18-1/8" X 21" BHA / SBM / Cement | 2026-02-24 | 2026-02-27 05:15 | 2026-03-01 17:15 | 60 | 2026-03-02 02:15 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 05a OSV - 30 hrs - BHA/Csg Tools/Pallet Material/Misc. | 2026-03-04 | 2026-03-06 14:00 | 2026-03-07 20:00 | 30 | 2026-03-08 05:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 06 OSV 60 Hours- 16-1/2" BHA / 14" Casing / SBM / Barite / Class H Cmt - BL 10.05" Csg & Excess 18" Csg | 2026-03-04 | 2026-03-06 21:00 | 2026-03-09 09:00 | 60 | 2026-03-09 18:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 06c OSV - 48 Hours - 14" Casing Overflow | 2026-03-07 | 2026-03-10 16:00 | 2026-03-12 16:00 | 48 | 2026-03-13 01:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07 OSV 60 Hours- 12 1/4" BHA / 11-7/8" Casing / SBM / Barite / TXI Cmt | 2026-03-14 | 2026-03-17 15:00 | 2026-03-20 03:00 | 60 | 2026-03-20 12:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07b OSV - 24 Hours - 5k bbls -14.1 ppg SBM | 2026-03-18 | 2026-03-20 | 2026-03-21 | 24 | 2026-03-21 09:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07d OSV 3 Hours - Stena (5) Jnts 6-5/8" HDWP / SLB B/U BHA (Share to Drop Off, If Available) | 2026-03-18 | 2026-03-19 06:00 | 2026-03-19 09:00 | 3 | 2026-03-19 18:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 07f OSV- 24 hrs- Backload Wireline Equipment / Groceries / Rig Supplies/ BL Riser | 2026-03-31 | 2026-04-01 22:00 | 2026-04-02 22:00 | 24 | 2026-04-03 07:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08 OSV - 60 Hours - 10-5/8" BHA / 7-5/8" Liner | 2026-04-08 | 2026-04-09 17:00 | 2026-04-12 05:00 | 60 | 2026-04-12 14:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08b OSV - 36 Hours - 1900 BBLS 11.9 SBM Riding / Backload 14.3 SBM / Backload (5) Jnts Riser / Misc. | 2026-04-13 | 2026-04-15 13:00 | 2026-04-17 01:00 | 36 | 2026-04-17 10:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 08f OSV 3 Hours - SLB BHA / WFR Fishing Tools / Cutting Boxes (Share to Drop Off) | 2026-04-19 | 2026-04-20 22:00 | 2026-04-21 01:00 | 3 | 2026-04-21 10:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 09 OSV- 30 hrs- Misc. / BH 14.2 SBM / BH Excess 11-7/8" Csg | 2026-04-27 | 2026-04-29 10:57 | 2026-04-30 16:57 | 30 | 2026-05-01 01:57 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 09b 0SV - 50 hrs - 7-5/8" x 10-3/4" Tieback Liner / BH Remaining 14.2 SBM | 2026-04-30 | 2026-05-05 05:00 | 2026-05-06 11:00 | 30 | 2026-05-06 20:00 | 9
Complete | Stena Evolution | Kaikias KI-2 Drill New Well | GL 10 OSV - 48 Hours - Workstrings 4-1/2", 6-5/8" DP / Demob Misc. Equipment | 2026-05-09 | 2026-05-12 07:00 | 2026-05-14 19:00 | 60 | 2026-05-15 04:00 | 9
Complete | Stena Evolution | Kaikias Completion | GL 01 OSV - 60 Hours - THS / Brine / Filtration / Misc. | 2026-05-12 | 2026-05-15 22:45 | 2026-05-18 10:45 | 60 | 2026-05-18 19:45 | 9
Complete | Stena Evolution | Kaikias Completion | GL 03 OSV 48 Hours - WBRT / HES CPS / HES CWT/4-1/2" Production Tbg/Sump Packer/ CIBP / Wireline | 2026-05-20 | 2026-05-23 16:15 | 2026-05-24 16:15 | 24 | 2026-05-25 01:15 | 9
Complete | Stena Evolution | Kaikias Completion | GL 04 OSV- 24 Hours - TCP / Lower Completion / Backload (11-12K) 11.9 PPG SBM & Trash Fluid | 2026-05-21 | 2026-05-24 17:30 | 2026-05-26 17:30 | 48 | 2026-05-27 02:30 | 9
Complete | Stena Evolution | Kaikias Completion | GL 05 OSV - 48 hrs- FMC / ROCS / Superior / Halliburton CPS & WBCO / SLB Prod. Pkr. / NaCl/MEG 8.9 | 2026-05-31 | 2026-06-03 09:00 | 2026-06-05 09:00 | 48 | 2026-06-05 18:00 | 9
Planned | Stena Evolution | Kaikias Completion | GL 07 OSV - 60 Hours - SSXT / Superior Powerwire / Misc. | 2026-06-10 | 2026-06-12 07:54 | 2026-06-14 07:54 | 48 | 2026-06-14 16:54 | 9
Planned | Stena Evolution | Kaikias Completion | GL 08c OSV- 30 Hours - Demob / Misc Cargo / Sparta 203 Drill Pipe | 2026-06-16 | 2026-06-17 06:00 | 2026-06-18 12:00 | 30 | 2026-06-18 21:00 | 9
Planned | Stena Evolution | Sparta SP203- Bypass | GL 01 OSV-36 Hours- Packer Retrieval / WBCO / SBM / Cement / Drill Pipe | 2026-06-17 | 2026-06-19 19:00 | 2026-06-21 07:00 | 36 | 2026-06-22 02:00 | 19
Planned | Stena Evolution | Sparta SP203- Bypass | GL 03 OSV-60 Hours- 10.05" Doubles & Singles / Cement | 2026-06-28 | 2026-06-30 17:00 | 2026-07-03 05:00 | 60 | 2026-07-04 | 19
Planned | Stena Evolution | Sparta SP203- Bypass | GL 04 OSV-48 Hours- Tieback Casing | 2026-07-03 | 2026-07-06 07:00 | 2026-07-08 07:00 | 48 | 2026-07-09 02:00 | 19
Planned | Stena Evolution | Sparta SP203- Bypass | GL 04a OSV 30 Hours - Expert Riser (21 joints Riser) | 2026-07-09 | 2026-07-10 07:00 | 2026-07-11 13:00 | 30 | 2026-07-12 08:00 | 19
Planned | Stena Evolution | Sparta SP203- Bypass | GL 05 OSV-36 Hours- Tubing Head Spool | 2026-07-16 | 2026-07-18 02:30 | 2026-07-19 14:30 | 36 | 2026-07-20 09:30 | 19
Complete | Q5000 | Whale WN213 PLT | OSV #1 - 50 hrs Mobilize | 2026-03-14 | 2026-03-15 08:00 | 2026-03-17 08:00 | 48 | 2026-03-17 11:00 | 3
Complete | Q5000 | Whale WN213 PLT | OSV #2- 36 hrs Mobilize and Transit | 2026-03-16 | 2026-03-17 08:00 | 2026-03-18 20:00 | 36 | 2026-03-18 23:00 | 3
Complete | Q5000 | Whale WN213 PLT | OSV - Latch and Test IRS - Brine, W/L Tools | 2026-03-20 | 2026-03-22 08:00 | 2026-03-27 08:00 | 120 | 2026-03-29 04:00 | 44
Complete | Q5000 | Whale WN303 PLT | GL 06 PLT B/h Base/Crude | 2026-03-31 | 2026-04-02 12:00 | 2026-04-06 12:00 | 96 | 2026-04-08 08:00 | 44
Complete | Q5000 | URSA Princess P002 Zonal Isolation | OSV 60 hrs - CT, Fluids, CMT | 2026-04-12 | 2026-04-13 21:00 | 2026-04-15 21:00 | 48 | 2026-04-16 06:00 | 9
Complete | Q5000 | URSA Princess P002 Zonal Isolation | Rig Up America with Tank Package | 2026-03-27 | 2026-04-20 01:00 | 2026-04-24 01:00 | 96 | 2026-04-24 10:00 | 9
Complete | Q5000 | Princess P101 | GL17a Milk Run | 2026-04-30 | 2026-05-02 06:00 | 2026-05-04 06:00 | 48 | 2026-05-04 16:00 | 10
Planned | Noble Voyager | Voyager Arrival in GoA | GL 03 OSV - Landing String, Grocereiss, Supplies | 2026-07-23 | 2026-07-25 | 2026-07-27 | 48 | 2026-07-27 12:00 | 12
Planned | Noble Voyager | NVOY Dummy Well - Rig Acceptance | GL 02 OSV - Backload Marine Riser 50jts | 2026-07-26 | 2026-07-28 12:00 | 2026-07-30 12:00 | 48 | 2026-07-31 | 12
Planned | Noble Voyager | Princess P13 - Top Hole | GL 01 OSV - 36hrs - 38 & 32" Csg, LPWH Tools, CTRS, WBM, CMT | 2026-07-26 | 2026-07-28 | 2026-07-29 12:00 | 36 | 2026-07-29 22:00 | 10
Planned | Noble Voyager | Princess P13 - Top Hole | GL 03 OSV - 60hrs - WBM, Foam & N2 Equip, 28" Csg, CTRS, WH Tools | 2026-07-28 | 2026-07-30 | 2026-08-01 12:00 | 60 | 2026-08-01 22:00 | 10
Planned | Noble Voyager | Princess P13 - Top Hole | GL 06 OSV - 72hrs - WBM, CMT, 22" Csg, HPWHH, Empty Baskets | 2026-07-31 | 2026-08-02 | 2026-08-05 | 72 | 2026-08-05 10:00 | 10
Planned | Noble Voyager | Princess P13 - Top Hole | GL 07 OSV - 72hrs - WBM, Empty Baskets, N2 Tanks, Foam Chemical | 2026-08-01 | 2026-08-02 | 2026-08-05 | 72 | 2026-08-05 10:00 | 10
Planned | Noble Voyager | Princess P13 - Top Hole | GL 08 OSV - 60hrs - Backload WBM & Equipment | 2026-08-03 | 2026-08-04 | 2026-08-06 12:00 | 60 | 2026-08-06 22:00 | 10
Planned | Noble Voyager | Princess P8 TA - Prep for Sidetrack | GL 01 OSV - 36hrs - SBM, Barite, CMT, BOPA, WH Tools, WBCO, 4-1/2" & 3-1/2" DP | 2026-08-03 | 2026-08-04 | 2026-08-05 12:00 | 36 | 2026-08-05 22:00 | 10
Planned | Noble Voyager | Princess P8 TA - Prep for Sidetrack | GL 02 OSV - WL Unit, Whipstock/Mills, Gyro, EZSVs, 10-3/4" Brute Pkr | 2026-08-12 | 2026-08-14 04:00 | 2026-08-15 16:00 | 36 | 2026-08-16 02:00 | 10
Planned | Noble Voyager | Princess P8 Drill - Sidetrack 02 - | GL 01 OSV - 30hrs - 6.25" BHAs, 5-1/2" Csg, Cents | 2026-08-17 | 2026-08-18 10:00 | 2026-08-19 16:00 | 30 | 2026-08-20 02:00 | 10
Complete | Mars | A23 Decomplete | GL 02 OSV_ 48 hrs. POOH with current tubing and accessories | 2026-05-17 | 2026-05-18 00:30 | 2026-05-20 00:30 | 48 | 2026-05-20 10:30 | 10
Complete | Mars | A23 Decomplete | GL 03 OSV - 60hrs - .Set EZSV-B Cement Retainer, SpotBalanced Plug | 2026-05-20 | 2026-05-22 18:00 | 2026-05-25 06:00 | 60 | 2026-05-25 16:00 | 10
Complete | Mars | A23 Slot Recovery | GL 02 OSV - 80hrs - Cut Tiebacks and Pull Upper Tieback | 2026-05-26 | 2026-05-28 18:00 | 2026-06-01 02:00 | 80 | 2026-06-01 02:00 | 10
Complete | Mars | A23 Slot Recovery | GL 04 OSV - 100hrs - Pull Production Riser | 2026-05-28 | 2026-05-30 06:00 | 2026-06-03 10:00 | 100 | 2026-06-01 02:00 | 10
Planned | Olympus | MB 09 | GL 05b Backhaul ODR to Core | 2026-06-20 | 2026-06-22 21:00 | 2026-06-25 21:00 | 72 | 2026-06-26 21:00 | 24
Planned | Olympus | MB 09 | GL 05c Outer Production Riser | 2026-06-22 | 2026-06-24 09:00 | 2026-06-27 09:00 | 72 | 2026-06-27 21:00 | 12
Planned | Olympus | MB 09 | GL 06 Run Upper Tieback | 2026-06-27 | 2026-06-28 09:00 | 2026-07-01 21:00 | 84 | 2026-07-02 09:00 | 12
Planned | Olympus | MB 09 Completions | GL 01 Set Sump Packer on E-line | 2026-06-29 | 2026-06-30 13:30 | 2026-07-02 01:30 | 36 | 2026-07-02 13:30 | 12
Planned | Olympus | MB 09 Completions | GL 03 Install Lower Completion | 2026-07-05 | 2026-07-06 19:00 | 2026-07-08 07:00 | 36 | 2026-07-08 19:00 | 12
Planned | Olympus | MB 09 Completions | GL 05 Install Upper Completion, Install Hanger | 2026-07-10 | 2026-07-11 | 2026-07-12 12:00 | 36 | 2026-07-13 | 12
Planned | Olympus | MB 09 Completions | GL 07 Set MLTH, displace well | 2026-07-14 | 2026-07-15 21:00 | 2026-07-17 09:00 | 36 | 2026-07-17 21:00 | 12
Complete | Q5000 | P101 | IWOCS, SLB CT | 2026-05-20 | 2026-05-22 | 2026-05-22 10:00 | 10 | 2026-05-22 20:00 | 10
Complete | Q5000 | P101 | Crawfish Run (Crew Boat) | 2026-05-21 | 2026-05-23 | 2026-05-22 10:00 | 5 | 2026-05-22 15:00 | 5
Complete | Q5000 | P101 | GL09 Milk Run (Crew Boat) | 2026-05-24 | 2026-05-26 | 2026-05-26 05:00 | 5 | 2026-05-26 10:00 | 5
Complete | Q5000 | P101 | MC940 Vito- GL01 Mobilize/Transit | 2026-05-28 | 2026-05-30 | 2026-05-30 10:00 | 10 | 2026-05-30 20:00 | 10
Planned | ESA | P&A | 2026 Well Services | 2026-08-27 | 2026-09-01 06:00 | 2027-01-01 06:00 | 2928 | 2027-01-01 14:00 | 8
Planned | Pontus | Sisco 001 Drill | GL 01 OSV / 36 hrs / 10,000 bbl of 16 ppg WBM, WBM Chemicals, 38" Jet Pipe; Jet & 32" BHA, 38" LPWHH, 38" Casing Tools, 28" Casing, Class H Cement | 2026-06-13 | 2026-06-17 06:45 | 2026-06-18 18:45 | 36 | 2026-06-19 10:45 | 16
Planned | Pontus | Sisco 001 Drill | GL 02 OSV / 24 hrs / 26" BHA, 28" Conductor, 28" Casing Tools, 28" Backups, 5,000 bbl of 16 ppg WBM, 1,500 Sacks of Gel **MC477** | 2026-06-15 | 2026-06-18 06:15 | 2026-06-19 06:15 | 24 | 2026-06-19 22:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 04 OSV / 36 hrs / 10,000 bbl of 16 ppg WBM, 22" Casing, 22" Casing Tools, 22" HPWHH | 2026-06-18 | 2026-06-20 17:15 | 2026-06-22 05:15 | 36 | 2026-06-22 21:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 05 OSV / 48 hrs / 15,000 bbl of 16 ppg WBM | 2026-06-19 | 2026-06-22 02:45 | 2026-06-24 02:45 | 48 | 2026-06-24 18:45 | 16
Planned | Pontus | Sisco 001 Drill | GL 07 OSV / 24 hrs / TBD bbl of TBD ppg SBM, SBM Chemicals, 18-1/8" x 21" BHA, 18" Casing, 18" Liner Hanger | 2026-06-24 | 2026-06-26 10:15 | 2026-06-27 10:15 | 24 | 2026-06-28 02:15 | 16
Planned | Pontus | Sisco 001 Drill | GL 11 OSV / 24 hrs / 12-1/4" & 11.97" Casing, Casing Rack Back Tools, 12-1/4" Hanger | 2026-07-05 | 2026-07-07 01:22 | 2026-07-08 01:22 | 24 | 2026-07-08 17:22 | 16
Planned | Pontus | Sisco 001 Drill | GL **CONTINGENCY** OSV / 24 hrs / 16" Casing, 16" Casing Tools, 16" Liner Hanger | 2026-07-07 | 2026-07-09 01:22 | 2026-07-10 01:22 | 24 | 2026-07-10 17:22 | 16
Planned | Pontus | Sisco 001 Drill | GL **CONTINGENCY** OSV / 24 hrs / 9-3/8" Casing, 9-3/8" Casing Tools, 9-3/8" Liner Hanger | 2026-07-15 | 2026-07-17 17:06 | 2026-07-18 17:06 | 24 | 2026-07-19 09:06 | 16
Planned | Q5000 | OWIRS Demobilization | OWIRS Demobilization (Extra Boat Required) | 2026-06-20 | 2026-06-22 06:00 | 2026-06-24 06:00 | 48 | 2026-06-24 12:00 | 6
Planned | Perdido | GA23 Slot Recovery | GL 01 OSV / slot recovery equipment | 2026-06-18 | 2026-06-21 20:00 | 2026-06-28 20:30 | 168.5 | 2026-06-30 08:30 | 36
Planned | Perdido | GA23 Drill Bypass | GL 02 Post Idle Period ll Drill 12 1/4" hole section | 2028-06-26 | 2026-06-28 20:30 | 2026-07-04 05:30 | 129 | 2026-07-05 17:30 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 05 OSV / H&P 2nd start up vessel 96 Hours | 2026-06-13 | 2026-06-16 06:00 | 2026-06-20 06:00 | 96 | 2026-06-21 18:00 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 10 FUTURE CAISSON OSV: Phase 1, startup and pull 2-7/8" | 2026-11-01 | 2026-11-04 06:00 | 2026-11-08 06:00 | 96 | 2026-11-09 18:00 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 11 FUTURE CAISSON OSV: Phase 2, Pull 7-5/8" & ESP | 2026-11-08 | 2026-11-08 06:00 | 2026-11-12 06:00 | 96 | 2026-11-13 18:00 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 12 FUTURE CAISSON OSV: Phase X1, Clean Out Run (if required) | 2026-11-15 | 2026-11-18 06:00 | 2026-11-22 06:00 | 96 | 2026-11-23 18:00 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 13 FUTURE CAISSON OSV: Phase X2, Waireline caisson caliper log | 2026-11-22 | 2026-11-25 06:00 | 2026-11-29 06:00 | 96 | 2026-11-30 18:00 | 36
Planned | Perdido | H&P 205 Rig Idle | GL 14 FUTURE CAISSON OSV: Phase 3 , Rerun ESP & Tbg | 2026-11-29 | 2026-12-02 06:00 | 2026-12-06 06:00 | 96 | 2026-12-07 18:00 | 36
Planned | Mars | A-23 Slot Recovery | GL 07 Install 13-5/8" TA Packer, N/D BOPs, Run Inner Drilling Riser | 2026-06-16 | 2026-06-18 14:00 | 2026-06-20 02:00 | 36 | 2026-06-20 14:00 | 12
Planned | Mars | A-23 St2 Drill | GL 01 Exit 13-3/8" Casing | 2026-06-19 | 2026-06-21 13:30 | 2026-06-23 01:30 | 36 | 2026-06-23 13:30 | 12
Planned | Mars | A-23 St2 Drill | GL 02 Drill 12.25" x 14.75" Hole section | 2026-06-24 | 2026-06-26 22:00 | 2026-06-28 10:00 | 36 | 2026-06-28 22:00 | 12
Planned | Mars | A-23 St2 Drill | GL 03 Run 11-7/8" Liner and Cement | 2026-06-30 | 2026-07-02 09:00 | 2026-07-03 21:00 | 36 | 2026-07-04 09:00 | 12
Planned | Mars | A-23 St2 Drill | GL 04 Drill 10.625" Pilot Hole section | 2026-07-03 | 2026-07-14 05:30 | 2026-07-15 17:30 | 36 | 2026-07-16 05:30 | 12
Planned | Mars | A-23 St2 Drill | GL 05 Abandon 10.625" Pilot Hole | 2026-07-12 | 2026-07-14 05:30 | 2026-07-15 17:30 | 36 | 2026-07-16 05:30 | 12
Planned | Mars | A-23 St2 Drill | GL 06 Drill 10.625" Sidetrack Hole section | 2026-07-16 | 2026-07-18 04:30 | 2026-07-19 16:30 | 36 | 2026-07-20 04:30 | 12
Planned | Mars | A-23 St2 Drill | GL 07 Install 7-5/8" Liner | 2026-07-21 | 2026-07-23 17:30 | 2026-07-25 05:30 | 36 | 2026-07-25 17:30 | 12
Planned | Mars | A-23 St2 Drill | GL 08 TA Well and Pull Inner Drilling Riser | 2026-07-27 | 2026-07-29 15:30 | 2026-07-31 03:30 | 36 | 2026-07-31 15:30 | 12
Planned | Mars | A-23 St2 Drill | GL 09 Install Lower Tieback | 2026-08-01 | 2026-08-03 20:00 | 2026-08-05 08:00 | 36 | 2026-08-05 20:00 | 12
Planned | Mars | A-23 St2 Drill | GL 10 TA Well, Pull ODR, Run Production Riser | 2026-08-04 | 2026-08-06 18:00 | 2026-08-08 06:00 | 36 | 2026-08-08 18:00 | 12
Planned | Mars | A-23 St2 Drill | GL 11 Run Upper Tieback | 2026-08-11 | 2026-08-13 11:30 | 2026-08-14 23:30 | 36 | 2026-08-15 11:30 | 12
Planned | Q5000 | Vito VA-12 Drift/ CTCO/ Stim | GL 02 Harvey America- Milk Run and Rig Fuel | 2026-06-11 | 2026-06-12 | 2026-06-14 | 48 | 2026-06-14 06:00 | 6
Planned | Q5000 | Vito VA-11 Drift/ CTCO | GL 03 OSV Pre-Mob OWIRS and Groceries | 2026-06-18 | 2026-06-19 | 2026-06-21 | 48 | 2026-06-21 06:00 | 6
Planned | Q5000 | Vito VA-11 Drift/ CTCO to VA-10 | Dark Vision for VA-10 | 2026-06-18 | 2026-06-19 | 2026-06-21 | 48 | 2026-06-21 06:00 | 6
Planned | Q5000 | Vito VA-10 Drift/ CTCO | GL 04 FSV/OSV Complete De-Mob (Groceries and Supplies) | 2026-06-25 | 2026-06-26 06:00 | 2026-06-28 06:00 | 48 | 2026-06-28 12:00 | 6
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18
Planned | [6 empty] | 24 |  | 18

## Reference
Valid Statuses | Column Descriptions
Complete | Status | Complete, In Progress, Planned, On Hold, Cancelled
In Progress | Asset | Platform/rig name (Pontus, Poseidon, etc.)
Planned | Project | Well/campaign name
On Hold | Activity | Description of cargo/scope (e.g., GL 01 OSV / 24 hrs / ...)
Cancelled | Base Delivery Date | Sail date from port (YYYY-MM-DD)
| Offshore Req Date | Arrival at rig (YYYY-MM-DD HH:MM)
| Offloading Complete Date | Departure from rig (YYYY-MM-DD HH:MM)
| Estimated Duration | Hours at offshore location
| Back to Port | Arrival back at port (YYYY-MM-DD HH:MM)
| Transit Time | Transit hours from offshore to port