## Spot Hire Update
Asset | Vessel Count | Area | Activity | Phase | Start Date | End Date | Status | Notes
Mars | 1 | Mars Corridor | A22 Completion | Completion | 2026-12-02 | 2026-01-10 | Complete
Olympus | 1 | Mars Corridor | MB24 Completion | Completion | 2026-01-01 | 2026-01-20 | Complete
Thalassa | 2 | Whale | WS304 Completion | Completion | 2026-12-01 | 2026-01-22 | Complete
Proteus | 2 | Vicksburg | VX004 Top Hole | Top Hole | 2026-01-14 | 2026-01-24 | Complete
Pontus | 1 | Perdido | GB004 PA | PA | 2026-01-01 | 2026-01-27 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-01-01 | 2026-01-31 | Complete
Stena Evolution | 1 | Sparta | SP203 15k Deepening | Deepening | 2026-12-06 | 2026-02-24 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Perdido | 1 | Perdido | GA-23 Deepening | Deepening | 2026-01-01 | 2026-03-13 | Complete
Poseidon | 2 | Whale | LWX 8 Completion | Deepening | 2026-01-29 | 2026-03-27 | Complete
Vito | 1 | Mars Corridor | WF SURF | Other | 2026-02-25 | 2026-03-31 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Q5000 | 1 | Whale | Whale 213, Whale 303 PLT Interventions | Intervention | 2026-03-15 | 2026-04-04 | Complete
Poseidon | 1 | Whale | HOS Carolina - Frac Boat | Frac Spot Hire | 2026-07-15 | 2026-04-30 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Poseidon | 2 | Whale | LWX 9 Completion | Completion | 2026-03-27 | 2026-05-10 | Complete
Stena Evolution | 2 | Kaikias | Kaikias KI-2 Drill New Well | Deepening | 2026-02-13 | 2026-05-18 | Complete
Whale | 1 | Whale | Whale TAR Warehouse Boat | TA | 2026-04-21 | 2026-05-31 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Stena Evolution | 2 | Kaikias | Kaikias KI-2 Completion | Completion | 2026-05-18 | 2026-06-20 | Planned
Olympus | 1 | Mars Corridor | A23 Slot Recovery | Deepening | 2026-05-24 | 2026-06-21 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Planned
Mars | 1 | Mars Corridor | MB09 Side Track | Deepening | 2026-04-28 | 2026-07-01 | Planned
Mars | 1 | Mars Corridor | MB09 Completion | Completion | 2026-07-01 | 2026-07-19 | Planned
Stena Evolution | 2 | Sparta | Sparta SP 203 Drill Bypass | Deepening | 2026-06-20 | 2026-07-24 | Planned
Poseidon | 2 | Whale | LWX 10 Deepening | Deepening | 2026-05-10 | 2026-07-10 | Planned
Pontus | 2 | Perdido | Sisco 001 Drill New Well | Deepening | 2026-06-18 | 2026-07-29 | Planned
Pontus | 2 | Dover | Dover 2 Drill New Well | Deepening | 2026-06-17 | 2026-07-29 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Noble Voyager | 2 | Princess | P13 Top Hole | Top Hole | 2026-07-22 | 2026-08-06 | Planned
Poseidon | 2 | Whale | LWX 10 Completion | Completion | 2026-07-10 | 2026-08-09 | Planned
Poseidon | 2 | Whale | UWX1 Top Hole | Top Hole | 2026-08-08 | 2026-08-15 | Planned
Olympus | 1 | Mars Corridor | A23 Drill | Deepening | 2026-06-21 | 2026-08-18 | Planned
Noble Voyager | 2 | Princess | Princess P8 Sidetrack | Deepening | 2026-08-06 | 2026-08-31 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Enchilada | 1 | Central Assets | Storm Choke well services | Other | 2026-09-01 | 2026-12-31 | Planned
Salsa | 1 | Central Assets | Abandonment | PA | 2026-09-01 | 2026-12-31 | Planned

## Reference
Valid Phases | Valid Statuses
EV Run | Planned
Top Hole | In Progress
Deepening | Completed
Completion | On Hold
Demob | Cancelled
PA
TA
Dedicated Run
Frac Spot Hire
Other