## Spot Hire Update
Asset | Vessel Count | Area | Activity | Phase | Start Date | End Date | Status | Notes
Mars | 1 | Mars Corridor | A22 Completion | Completion | 2026-12-02 | 2026-01-10 | Complete
Olympus | 1 | Mars Corridor | MB24 Completion | Completion | 2026-01-01 | 2026-01-20 | Complete
Thalassa | 2 | Whale | WS304 Completion | Completion | 2026-12-01 | 2026-01-22 | Complete
Proteus | 2 | Vicksburg | VX004 Top Hole | Top Hole | 2026-01-14 | 2026-01-24 | Complete
Pontus | 1 | Perdido | GB004 PA | PA | 2026-01-01 | 2026-01-27 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-01-01 | 2026-01-31 | Complete
Stena Evolution | 1 | Sparta | SP203 15k Deepening | Deepening | 2026-12-06 | 2026-02-24 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-02-01 | 2026-02-28 | Complete
Perdido | 1 | Perdido | GA-23 Deepening | Deepening | 2026-01-01 | 2026-03-13 | Complete
Poseidon | 2 | Whale | LWX 8 Completion | Deepening | 2026-01-29 | 2026-03-27 | Complete
Vito | 1 | Mars Corridor | WF SURF | Other | 2026-02-25 | 2026-03-31 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-03-01 | 2026-03-31 | Complete
Q5000 | 1 | Whale | Whale 213, Whale 303 PLT Interventions | Intervention | 2026-03-15 | 2026-04-04 | Complete
Poseidon | 1 | Whale | HOS Carolina - Frac Boat | Frac Spot Hire | 2026-07-15 | 2026-04-30 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-04-01 | 2026-04-30 | Complete
Poseidon | 2 | Whale | LWX 9 Completion | Completion | 2026-03-27 | 2026-05-10 | Complete
Stena Evolution | 2 | Kaikias | Kaikias KI-2 Drill New Well | Deepening | 2026-02-13 | 2026-05-18 | Complete
Whale | 1 | Whale | Whale TAR Warehouse Boat | TA | 2026-04-21 | 2026-05-31 | Complete
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-05-01 | 2026-05-31 | Complete
Stena Evolution | 2 | Kaikias | Kaikias KI-2 Completion | Completion | 2026-05-18 | 2026-06-20 | Complete
Olympus | 1 | Mars Corridor | A23 Slot Recovery | Deepening | 2026-05-24 | 2026-06-21 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Complete
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Complete
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-06-01 | 2026-06-30 | Complete
Mars | 1 | Mars Corridor | MB09 Side Track | Deepening | 2026-04-28 | 2026-07-01 | Planned
Poseidon | 2 | Whale | LWX 10 Deepening | Deepening | 2026-05-10 | 2026-07-12 | Planned
Mars | 1 | Mars Corridor | MB09 Completion | Completion | 2026-07-01 | 2026-07-19 | Planned
Stena Evolution | 2 | Sparta | Sparta SP 203 Drill Bypass | Deepening | 2026-06-21 | 2026-07-31 | Planned
Pontus | 2 | Perdido | Sisco 001 Drill New Well | Deepening | 2026-06-18 | 2026-08-04 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-07-01 | 2026-07-31 | Planned
Pontus | 2 | Dover | Dover 2 Drill New Well | Deepening | 2026-06-18 | 2026-08-03 | Complete
Poseidon | 2 | Whale | LWX 10 Completion | Completion | 2026-07-12 | 2026-08-11 | Planned
Olympus | 1 | Mars Corridor | A23 Drill | Deepening | 2026-06-21 | 2026-08-18 | Planned
Noble Voyager | 3 | Princess | Ursa North P013 Top Hole | Top Hole | 2026-07-22 | 2026-08-18 | Planned
Poseidon | 3 | Whale | UWX1 Top Hole | Top Hole | 2026-08-11 | 2026-08-18 | Planned
Stena Evolution | 2 | Sparta | Sparta SP106 Deepen Hole | Deepening | 2026-07-31 | 2026-09-03 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-08-01 | 2026-08-31 | Planned
Noble Voyager | 2 | Princess | Princess P8 Sidetrack | Deepening | 2026-08-18 | 2026-09-13 | Planned
Poseidon | 2 | Whale | UWX1 Deepen Hole | Deepening | 2026-08-18 | 2026-09-14 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-09-01 | 2026-09-30 | Planned
Noble Voyager | 2 | Princess | Princess P8 Completion | Completion | 2026-09-13 | 2026-10-03 | Planned
Noble Voyager | 2 | Ursa | Ursa North P013 Deepening | Deepening | 2026-10-03 | 2026-10-23 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-10-01 | 2026-10-31 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-11-01 | 2026-11-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-01-01 | 2026-12-30 | Planned
ESA, Ursa | 1 | Central Assets | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Appomatox, Vito, Olympus | 1 | East Asset | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Perdido/Whale | 1 | West Assets | EV Run | EV Run | 2026-12-01 | 2026-12-31 | Planned
Enchilada | 1 | Central Assets | Storm Choke well services | Other | 2026-09-01 | 2026-12-31 | Planned
Salsa | 1 | Central Assets | Abandonment | PA | 2026-09-01 | 2026-12-31 | Planned

## Reference
Valid Phases | Valid Statuses
EV Run | Planned
Top Hole | In Progress
Deepening | Completed
Completion | On Hold
Demob | Cancelled
PA
TA
Dedicated Run
Frac Spot Hire
Other

## Asset Pivot
Highest Vessel Count per Asset |  |  | Pivot: Highest Vessels by Asset |  | Asset | Activity | Max Vessels for Activity
[5 empty] | Appomatox, Vito, Olympus | EV Run | 1
Asset | Activity Used | Highest Vessel Count | Asset | Highest Vessel Count | Enchilada | Storm Choke well services | 1
Appomatox, Vito, Olympus | EV Run | 1 | Appomatox, Vito, Olympus | 1 | ESA, Ursa | EV Run | 1
Enchilada | Storm Choke well services | 1 | Enchilada | 1 | Mars | A22 Completion | 1
ESA, Ursa | EV Run | 1 | ESA, Ursa | 1 | Mars | MB09 Completion | 1
Mars | A22 Completion | 1 | Mars | 1 | Mars | MB09 Side Track | 1
Noble Voyager | Ursa North P013 Top Hole | 2 | Noble Voyager | 2 | Noble Voyager | Princess P8 Completion | 2
Olympus | MB24 Completion | 1 | Olympus | 1 | Noble Voyager | Princess P8 Sidetrack | 2
Perdido | GA-23 Deepening | 1 | Perdido | 1 | Noble Voyager | Ursa North P013 Deepening | 2
Perdido/Whale | EV Run | 1 | Perdido/Whale | 1 | Noble Voyager | Ursa North P013 Top Hole | 2
Pontus | Sisco 001 Drill New Well | 2 | Pontus | 2 | Olympus | A23 Drill | 1
Poseidon | LWX 8 Completion | 2 | Poseidon | 2 | Olympus | A23 Slot Recovery | 1
Proteus | VX004 Top Hole | 2 | Proteus | 2 | Olympus | MB24 Completion | 1
Q5000 | Whale 213, Whale 303 PLT Interventions | 1 | Q5000 | 1 | Perdido | GA-23 Deepening | 1
Salsa | Abandonment | 1 | Salsa | 1 | Perdido/Whale | EV Run | 1
Stena Evolution | Kaikias KI-2 Drill New Well | 2 | Stena Evolution | 2 | Pontus | Dover 2 Drill New Well | 2
Thalassa | WS304 Completion | 2 | Thalassa | 2 | Pontus | GB004 PA | 1
Vito | WF SURF | 1 | Vito | 1 | Pontus | Sisco 001 Drill New Well | 2
Whale | Whale TAR Warehouse Boat | 1 | Whale | 1 | Poseidon | HOS Carolina - Frac Boat | 1
[5 empty] | Poseidon | LWX 10 Completion | 2
[5 empty] | Poseidon | LWX 10 Deepening | 2
Method | First find MAX vessel count for each Asset + Activity |  |  |  | Poseidon | LWX 8 Completion | 2
Asset result |  |  |  |  | Poseidon | LWX 9 Completion | 2
[5 empty] | Poseidon | UWX1 Deepen Hole | 2
[5 empty] | Poseidon | UWX1 Top Hole | 2
[5 empty] | Proteus | VX004 Top Hole | 2
[5 empty] | Q5000 | Whale 213, Whale 303 PLT Interventions | 1
[5 empty] | Salsa | Abandonment | 1
[5 empty] | Stena Evolution | Kaikias KI-2 Completion | 2
[5 empty] | Stena Evolution | Kaikias KI-2 Drill New Well | 2
[5 empty] | Stena Evolution | SP203 15k Deepening | 1
[5 empty] | Stena Evolution | Sparta SP 203 Drill Bypass | 2
[5 empty] | Stena Evolution | Sparta SP106 Deepen Hole | 2
[5 empty] | Thalassa | WS304 Completion | 2
[5 empty] | Vito | WF SURF | 1
[5 empty] | Whale | Whale TAR Warehouse Boat | 1